## README
Ashish-format EVENTS sheet (v2) — Media / DataLabs / App
Built | 2026-09-07
Sample | Test workbook tab audit-template (gid 261893411)
Sample URL | https://docs.google.com/spreadsheets/d/1NCpTEzgEEtds0uCfqPNSS6aeFhOpKbgkL_F-cgtVPxg/edit?gid=261893411
Scope | EVENTS only + event property groups + custom event properties. NOT user properties.
Claude note | Session 198e6dd1: each row is Event + HOW (trigger_steps) + WHERE (trigger_url), not bare inventory.
Claude note | Session 9bb7d5bf: datalabs_onboarding_status / attribution_source gaps are USER-PROPERTY sheet issues — out of scope here. See user-properties workbook separately.
property values | inc42 = Media ¦ datalabs = DataLabs ¦ app = App
Empty cells | Unknown in source — not invented.
Sources | master.xlsx canonical + 29 Aug audits + New Events Found

## Media (Inc42)
event_group | event_name | display_name | property | trigger_steps | trigger_url | login_state | event_property_groups | custom_event_properties | trigger_identify_call | expected_traits | source | destinations | automatable | test_notes | description | audit_status | audit_date | audit_notes
page_view | Pageview | Pageview | inc42 | Open / navigate to the page ¦ page finishes loading ¦ event fires (Pageview) | https://inc42.com (any page) | any | content ¦ page |  | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude ¦ meta | auto |  | As soon as a page loads | Renamed | 2026-08-29 | PostHog: Y — 2,049,513 (90d) ¦ Customer.io: Y — 14% of profiles, used in 1 campaign ¦ Live name: $pageview (PostHog) / Page View (Customer.io) ¦ Update sheet to match reality — name differs on both destinations, and PostHog + Customer.io are entirely missing from the Destinations column despite being the two live vendors
content | Form Submission | Form Submission | inc42 | When the form is successfully submitted ¦ event `Form Submission` fires | https://inc42.com — form embed | any | content ¦ page | Modal Name Modal ID Modal Type | Yes |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude ¦ meta | auto |  | Modal Type | Confirmed correct | 2026-08-29 | PostHog: Y — 47,007 (90d) ¦ Customer.io: Y — 7% of profiles ¦ Live name: (same) ¦ Update sheet to match reality — add PostHog and Customer.io to Destinations column
monetization | Plus Lock | Plus Lock | inc42 | Plus lock gets triggered on the article page ¦ event `Plus Lock` fires | https://inc42.com — paywalled article | logged-in | content ¦ page | Modal Name Modal ID Modal Type | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitudel ¦ meta | manual |  | Modal Type | Broken-not firing | 2026-08-29 | PostHog: Y — 4 (90d, near-zero) ¦ Customer.io: N — not in Customer.io event catalog ¦ Live name: (same) ¦ Needs product owner decision — only 4 hits sitewide in 90 days; confirm if Plus Lock is still meant to exist or was superseded
user_engagement | Registered | Registered | inc42 | Open signup ¦ complete Auth0 registration ¦ land authenticated | https://inc42.com — signup / auth0 | logged-out | page | Not individually re-queried this run | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitudel ¦ meta | auto |  | When user registers on the platform | Confirmed correct | 2026-08-29 | PostHog: Y — 2,908 (90d) ¦ Customer.io: Y — 3% of profiles ¦ Live name: (same) ¦ Update sheet to match reality — add PostHog + Customer.io to Destinations
user_engagement | Login | Login | inc42 | Inc42 login success ¦ event `Login` fires | https://inc42.com — login modal | any | page | distinct_id resolves to the account email at the moment this event fires (identify() call) — see Part E identity finding for what happens after | Yes |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude | auto |  | Inc42 login success | Confirmed correct | 2026-08-29 | PostHog: Y — 10,501 (90d) ¦ Customer.io: Y — 5% of profiles ¦ Live name: (same) ¦ Update sheet to match reality — add PostHog + Customer.io to Destinations
user_engagement | Logout | Logout | inc42 | Manual logout on Inc42 account ¦ event `Logout` fires | https://inc42.com | any | page | Logout Status | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude | auto |  | Manual logout on Inc42 account | Confirmed correct | 2026-08-29 | PostHog: Y — 61 (90d) ¦ Customer.io: Y — <1% of profiles ¦ Live name: (same) ¦ Update sheet to match reality
ui_interaction | Modal Viewed | Modal Viewed | inc42 |  | https://inc42.com — modal overlay | any | content ¦ page | Modal Name Modal ID Modal Type | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude | auto |  | Modal Type | Confirmed correct | 2026-08-29 | PostHog: Y — 365,923 (90d) — 4th-highest-volume event in the project ¦ Customer.io: Y — 8% of profiles ¦ Live name: (same) ¦ Update sheet to match reality — top-5 volume PostHog event with zero documented destinations; add PostHog + Customer.io
content | My Inc42 | My Inc42 | inc42 | On page view within any page/tab of My Inc42 + On click on any tab from inside My Inc42 page ¦ event `My Inc42` fires | https://inc42.com | any | page | My Inc42 State | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude | auto |  | On page view within any page/tab of My Inc42 + On click on any tab from inside My Inc42 page | Broken-not firing | 2026-08-29 | PostHog: Y — 1 (90d, essentially dead) ¦ Customer.io: N — not in Customer.io catalog ¦ Live name: (same) ¦ Needs product owner decision — confirm if My Inc42 tab tracking was ever wired up
user_engagement | Newsletter Subscribed | Newsletter Subscribed | inc42 | Success NL Subscribed ¦ event `Newsletter Subscribed` fires | https://inc42.com — article footer / homepage / popup | logged-out | content ¦ page | Modal Name Modal ID Modal Type Daily_Newsletter_Status | Yes |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude ¦ meta | auto |  | Modal Type | Confirmed correct | 2026-08-29 | PostHog: Y — 3,264 (90d) ¦ Customer.io: Y — 5% of profiles, used in 1 live campaign ¦ Live name: (same) ¦ Update sheet to match reality
content | s | s | inc42 | Success NL Subscribed ¦ event `s` fires | https://inc42.com | any | content ¦ page | Modal Name Modal ID Modal Type Daily_Newsletter_Status | Yes |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude ¦ meta | auto |  | Modal Type | Dead-test event | 2026-08-29 | PostHog: N — no event named "s" in 90 days of PostHog data ¦ Customer.io: N — not in Customer.io catalog ¦ Live name: Never fires live under this name ¦ No action — confirmed accidental duplicate of the Newsletter Subscribed row (Part E.4); safe to delete this row
monetization | Plus Bottom Bar | Plus Bottom Bar | inc42 | Bottom bar triggered ¦ event `Plus Bottom Bar` fires | https://inc42.com/plus or paywall modal | logged-in | content ¦ page | n/a | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude | manual |  | Bottom bar triggered | Broken-not firing | 2026-08-29 | PostHog: N — not seen in 90 days ¦ Customer.io: N — not in Customer.io catalog ¦ Live name: n/a ¦ Needs product owner decision — confirm if this banner still exists on the site
content | ResetPassword | ResetPassword | inc42 | Reset password initiated ¦ event `ResetPassword` fires | https://inc42.com | any | page | Not individually re-queried this run | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude | auto |  | Reset password initiated | Confirmed correct | 2026-08-29 | PostHog: Y — 137 (90d) ¦ Customer.io: Y — <1% of profiles ¦ Live name: (same) ¦ Update sheet to match reality
user_engagement | Share | Share | inc42 | Social share button clicked ¦ event `Share` fires | https://inc42.com | any | content ¦ page | Share Platform | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude | auto |  | Social share button clicked | Confirmed correct | 2026-08-29 | PostHog: Y — 125 (90d) ¦ Customer.io: Y — <1% of profiles ¦ Live name: (same) ¦ Update sheet to match reality
monetization | Plus Payment Initiated | Plus Payment Initiated | inc42 | When user clicks pay now button ¦ event `Plus Payment Initiated` fires | https://inc42.com/plus or paywall modal | logged-in | page | Not individually re-queried this run | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitudel ¦ meta | manual |  | When user clicks pay now button | Confirmed correct | 2026-08-29 | PostHog: Y — 84 (90d) ¦ Customer.io: Y — <1% of profiles ¦ Live name: (same) ¦ Update sheet to match reality
ui_interaction | Private Mode Modal | Private Mode Modal | inc42 | Private Mode Modal Fired ¦ event `Private Mode Modal` fires | https://inc42.com — modal overlay | any | content ¦ page | Not individually re-queried this run | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude | auto |  | Private Mode Modal Fired | Confirmed correct | 2026-08-29 | PostHog: Y — 739,065 (90d) — 3rd-highest-volume event in the entire project ¦ Customer.io: Y — 3% of profiles ¦ Live name: (same) ¦ PRIORITY — update sheet to match reality; this is the 3rd-largest event PostHog receives sitewide and the sheet lists zero PostHog/Customer.io destinations for it
user_engagement | Plus Subscribed | Plus Subscribed | inc42 |  | https://inc42.com/plus or paywall modal | logged-out | 2 ¦ Plus | Not individually re-queried this run | Yes |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude ¦ meta | manual |  |  | Confirmed correct | 2026-08-29 | PostHog: Y — 38 (90d) ¦ Customer.io: Y — <1% of profiles, used in 1 campaign ¦ Live name: (same) ¦ Update sheet to match reality
monetization | Plus Checkout | Plus Checkout | inc42 | Fires when a user initiates plus subscription ¦ event `Plus Checkout` fires | https://inc42.com/plus or paywall modal | logged-in | page | Checkout State Plus Membership Type Plus Term ID | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude ¦ meta | manual |  | Fires when a user initiates plus subscription | Confirmed correct | 2026-08-29 | PostHog: Y — 657 (90d) ¦ Customer.io: Y — <1% of profiles ¦ Live name: (same) ¦ Update sheet to match reality
content | Cart Abandon | Cart Abandon | inc42 |  | https://inc42.com | any | page | n/a | No |  | web | mixpanel ¦ moengage ¦ amplitude ¦ meta | auto |  |  | Renamed | 2026-08-29 | PostHog: N — no "Cart Abandon" event live in PostHog ¦ Customer.io: Y — as "Cart Abandoned" and "Cart Abandoner", 2% of profiles ¦ Live name: Cart Abandoned / Cart Abandoner (Customer.io); no PostHog equivalent at all ¦ Update sheet to match reality — confirm the correct canonical name and that PostHog exclusion is intentional
ui_interaction | Recommendation Click | Recommendation Click | inc42 |  | https://inc42.com | any | content ¦ page | Recommendation Widget Source Recommendation Widget Type Recommendation Item Number | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude | auto |  |  | Confirmed correct | 2026-08-29 | PostHog: Y — 19,953 (90d) ¦ Customer.io: Y — 1% of profiles ¦ Live name: (same) ¦ Update sheet to match reality
user_engagement | Plus Onboarding | Plus Onboarding | inc42 |  | https://inc42.com/plus or paywall modal | logged-in | page | Plus Onboarding State | Yes |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude | manual |  |  | Confirmed correct but likely superseded | 2026-08-29 | PostHog: Y — 139 (90d) ¦ Customer.io: Y — <1% of profiles ¦ Live name: (same) ¦ Needs product owner decision — volume (139) is dwarfed by the unmapped "Inc42 Onboarding" event (14,960); confirm which is canonical
user_engagement | Follow | Follow | inc42 | On clicking a Follow button ¦ event `Follow` fires | https://inc42.com — company or author follow control | logged-in | page | Industry | No |  | web |  | auto |  | On clicking a Follow button | Confirmed correct | 2026-08-29 | PostHog: Y — 58 (90d) ¦ Customer.io: Y — <1% of profiles ¦ Live name: (same) ¦ Update sheet to match reality — Destinations column is blank in the sheet despite this event reaching both PostHog and Customer.io
user_engagement | Unfollow | Unfollow | inc42 | After unfollowing a topic ¦ event `Unfollow` fires | https://inc42.com — company or author follow control | logged-in | page | Industry | No |  | web |  | auto |  | After unfollowing a topic | Confirmed correct | 2026-08-29 | PostHog: Y — 4 (90d) ¦ Customer.io: Y — <1% of profiles ¦ Live name: (same) ¦ Update sheet to match reality
monetization | Cancel Plus Membership | Cancel Plus Membership | inc42 |  | https://inc42.com/plus or paywall modal | logged-in | page | Plus Cancellation State | No |  | web |  | manual |  |  | Broken-not firing | 2026-08-29 | PostHog: N — not seen in 90 days ¦ Customer.io: N — not in Customer.io catalog ¦ Live name: n/a ¦ Needs product owner decision
user_engagement | Save Story | Save Story | inc42 |  | https://inc42.com — article page bookmark control | logged-in | content ¦ page | Not individually re-queried this run | No |  | web |  | auto |  |  | Confirmed correct | 2026-08-29 | PostHog: Y — 41 (90d) ¦ Customer.io: Y — <1% of profiles ¦ Live name: (same) ¦ Update sheet to match reality
user_engagement | Unsave Story | Unsave Story | inc42 |  | https://inc42.com — article page bookmark control | logged-in | content ¦ page | Not individually re-queried this run | No |  | web |  | auto |  |  | Confirmed correct | 2026-08-29 | PostHog: Y — 6 (90d) ¦ Customer.io: Y — <1% of profiles ¦ Live name: (same) ¦ Update sheet to match reality
ui_interaction | Freewall Lock | Freewall Lock | inc42 |  | https://inc42.com | any | content ¦ page | Modal Name Modal ID Modal Type | No |  | web |  | auto |  | Modal Type | Property mismatch | 2026-08-29 | PostHog: Y — 144,692 (90d) ¦ Customer.io: Y — 5% of profiles ¦ Live name: (same) ¦ Fix production — Modal Name never populates on this event; also add PostHog + Customer.io to sheet Destinations
content | Guide View | Guide View | inc42 | A Guide was viewed ¦ event `Guide View` fires | https://inc42.com | any | content ¦ page | Not queried, statistically insignificant | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude | auto |  | A Guide was viewed | Broken-not firing | 2026-08-29 | PostHog: Y — 1 (90d, essentially dead) ¦ Customer.io: Y — <1% of profiles ¦ Live name: (same) ¦ Needs product owner decision
content | Report View | Report View | inc42 | A Report was viewed ¦ event `Report View` fires | https://inc42.com | any | page | n/a | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude | auto |  | A Report was viewed | Renamed | 2026-08-29 | PostHog: N — no "Report View" event live ¦ Customer.io: N — neither name in Customer.io catalog ¦ Live name: Report Interaction (PostHog only) — 1,505 hits but stopped firing after 2 Jul 2026 ¦ Needs product owner decision — confirm whether the Report feature was removed; if not, production is broken
page_view | Scroll Depth (Paused) | Scroll Depth (Paused) | inc42 |  | https://inc42.com — article body | any | content ¦ page | n/a, statistically insignificant | No |  | web | ga4 | auto |  |  | Broken-not firing | 2026-08-29 | PostHog: Y — 1 hit in 90 days (as "Scroll Depth", no "(Paused)" suffix) — effectively zero ¦ Customer.io: N — not in Customer.io catalog ¦ Live name: Scroll Depth ¦ PRIORITY (Part E.3) — fix production; restoring scroll depth is a locked company strategy item, not routine cleanup
content | Qr Scan | Qr Scan | inc42 |  | https://inc42.com | any |  | Not individually re-queried this run | No |  | web |  | auto |  |  | Confirmed correct | 2026-08-29 | PostHog: Y — 19 (90d) ¦ Customer.io: Y — <1% of profiles ¦ Live name: (same) ¦ Update sheet to match reality
search_action | Search Result Click | Search Result Click | inc42 | Search result clicked ¦ event `Search Result Click` fires | https://inc42.com — header search | any | page | n/a | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude | auto |  | Search result clicked | Renamed | 2026-08-29 | PostHog: N — no "Search Result Click" event live ¦ Customer.io: Y — as "Search Click", <1% of profiles ¦ Live name: Search Click ¦ Update sheet to match reality
search_action | Search Close | Search Close | inc42 | Seach close button clicked ¦ event `Search Close` fires | https://inc42.com — header search | any | content ¦ page | Not individually re-queried this run | No |  | web | ga4 ¦ mixpanel ¦ moengage ¦ amplitude | auto |  | Seach close button clicked | Property mismatch (PostHog only) | 2026-08-29 | PostHog: Y — 1,410 (90d) ¦ Customer.io: N — not in Customer.io catalog ¦ Live name: (same) ¦ Needs product owner decision — confirm if Customer.io was ever meant to receive this
search_action | Search Active | Search Active | inc42 | Search button click ¦ event `Search Active` fires | https://inc42.com — header search | any | page | Not individually re-queried this run | No |  | web |  | auto |  | Search button click | Confirmed correct | 2026-08-29 | PostHog: Y — 4,813 (90d) ¦ Customer.io: Y — 1% of profiles ¦ Live name: (same) ¦ Update sheet to match reality — Destinations blank in sheet
search_action | Search Completed | Search Completed | inc42 | Input of query in search bar ¦ event `Search Completed` fires | https://inc42.com — header search | any | page | Search Query | No |  | web |  | auto |  | Input of query in search bar | Property mismatch | 2026-08-29 | PostHog: Y — 25,925 (90d) ¦ Customer.io: Y — 2% of profiles ¦ Live name: (same) ¦ Fix production — verify result-count/search-scope equivalents are attached
search_action | Search Click | Search Click | inc42 | Click on search result ¦ event `Search Click` fires | https://inc42.com — header search | any | page | Search Query Result Count Index Result Type | No |  | web |  | auto |  | Click on search result | Confirmed correct | 2026-08-29 | PostHog: Y — 1,963 (90d) ¦ Customer.io: Y — <1% of profiles ¦ Live name: (same) ¦ Update sheet to match reality
content | User Segment | User Segment | inc42 | Open / navigate to the page ¦ page finishes loading ¦ event fires (User Segment) | https://inc42.com | any |  | Segment CampaignType CampaignAction | No |  | web | mixpanel ¦ moengage | auto |  | On Page Load if moengage returns value | Dead-test event | 2026-08-29 | PostHog: Y — 3 (90d, essentially dead) ¦ Customer.io: N — not in Customer.io catalog ¦ Live name: (same) ¦ Needs product owner decision — deprecate from the sheet; source integration no longer exists
user_engagement | Login Modal | Login Modal | inc42 | On "Login" button click ¦ event `Login Modal` fires | https://inc42.com — modal overlay | any | page | Action Login Method User Action | No |  | web | moengage ¦ posthog | auto |  | On "Login" button click | Property mismatch | 2026-08-29 | PostHog: Y — 36,002 (90d) ¦ Customer.io: Y — 8% of profiles ¦ Live name: (same) ¦ Fix production — Login Modal's 3 spec'd properties are all empty on live traffic; also add Customer.io to sheet Destinations (PostHog already correctly listed)
ui_interaction | Modal Close | Modal Close | inc42 |  | https://inc42.com — modal overlay | any |  | Modal Name / Modal Id / Modal Type (e.g. "Daily Brief" / "freewall-lock-v3" / "Newsletter RFV") | No |  | web | posthog | auto |  | Update sheet to match reality — add a row; this is a top-10 volume event | Confirmed correct | 2026-08-29 | Volume: ~70,000 (90d: 214,979)
ui_interaction | Modal Closed | Modal Closed | inc42 |  | https://inc42.com — modal overlay | any |  | Not individually queried | No |  | web | posthog | auto |  | Update sheet to match reality — add a row; distinct from both Modal Viewed and Modal Close | Confirmed correct | 2026-08-29 | Volume: ~14,000 (90d: 42,209)
ui_interaction | Modal Clicked | Modal Clicked | inc42 |  | https://inc42.com — modal overlay | any |  | Not individually queried | No |  | web | posthog | auto |  | Update sheet to match reality — add a row | Confirmed correct | 2026-08-29 | Volume: ~750 (90d: 2,243)
user_engagement | Inc42 Onboarding | Inc42 Onboarding | inc42 |  | https://inc42.com | any |  | Inc42 Onboarding State: "Onboarding Started" (2,750/14d), "Onboarding Step 1 Completed" (340/14d) | No |  | web | posthog | auto |  | Update sheet to match reality — add a row; likely the successor to Plus Onboarding, confirm with product owner | Confirmed correct | 2026-08-29 | Volume: ~5,000 (90d: 14,960 PostHog; 6% of Customer.io profiles)
monetization | Pro Payment | Pro Payment | inc42 |  | https://inc42.com/pro | any |  | Payment Stage, Pro Membership Type, DL Page Type, Slug — looks DataLabs/Pro-tier related, not Plus | No |  | web | posthog | auto |  | Needs product owner decision — confirm this belongs in the Media sheet at all, or is a DataLabs-owned event | Confirmed correct | 2026-08-29 | Volume: ~180 (90d: 548)
content | Report Interaction | Report Interaction | inc42 |  | https://inc42.com | any |  | No properties captured at all | No |  | web | posthog | auto |  | Needs product owner decision — likely the old name for Report View, now dead; confirm if the Report feature still exists | Dead-test event | 2026-08-29 | Volume: 0 in last 30d — stopped 2026-07-02
content | dl_event / gtm.js / session_start / first_visit / gtm.timer / user_engagement | dl_event / gtm.js / session_start / first_visit / gtm.timer / user_engagement | inc42 |  | https://inc42.com | any |  | GA4/GTM's own internal event names, not Media's custom taxonomy | No |  | web | posthog | auto |  | No action — looks like a one-off GTM/GA4 debug or dataLayer-bridge leak into the PostHog project, not a real production signal; flag to confirm it's not still wired up | Dead-test event | 2026-08-29 | Volume: 0 in last 30d — all 14 or fewer hits total, all from one URL on one day (4 Jul 2026)
monetization | ai_summit_teampass_purchased / aisummit_application_completed / aisummit_cart_abandoner | ai_summit_teampass_purchased / aisummit_application_completed / aisummit_cart_abandoner | inc42 |  | https://inc42.com | any |  | Not verified (Customer.io Data index doesn't expose raw payloads) | No |  | web | customerio | auto |  | No action — AI Summit event-registration campaign, not part of the core Media content taxonomy | Confirmed correct | 2026-08-29 | Volume: <1% of profiles each
monetization | DRS Lead Payment / DRS_Application_Completed / DRS_cart_abandoner | DRS Lead Payment / DRS_Application_Completed / DRS_cart_abandoner | inc42 |  | https://inc42.com | any |  | Not verified | No |  | web | customerio | auto |  | No action — DRS (Digital Report Summit or similar) campaign events, not part of the core Media content taxonomy | Confirmed correct | 2026-08-29 | Volume: <1% of profiles each
content | Lead | Lead | inc42 |  | https://inc42.com | any |  | Not verified | No |  | web | customerio | auto |  | No action — generic lead-gen event, likely from a landing-page form | Confirmed correct | 2026-08-29 | Volume: <1% of profiles
monetization | Purchase | Purchase | inc42 |  | https://inc42.com | any |  | Not verified | No |  | web | customerio | auto |  | Needs product owner decision — this is used in 6 live automations; confirm if it should be documented in the Media sheet as a real conversion event | Confirmed correct | 2026-08-29 | Volume: 1% of profiles, used in 1 campaign + 6 automations
page_view | Page View test | Page View test | inc42 | Navigate to page ¦ page load completes | https://inc42.com (any page) | any |  | Not verified | No |  | web | customerio | auto |  | No action — name confirms this is leftover test data | Dead-test event | 2026-08-29 | Volume: <1% of profiles
Note on E1: HOW it fires: user/system steps, pipe-separated (Ashish sample style)
Note on F1: WHERE it fires: URL or app screen/component

## DataLabs
event_group | event_name | display_name | property | trigger_steps | trigger_url | login_state | event_property_groups | custom_event_properties | trigger_identify_call | expected_traits | source | destinations | automatable | test_notes | description | audit_status | audit_date | audit_notes
user_engagement | Registered | Registered | datalabs | Open signup ¦ complete Auth0 registration ¦ land authenticated | https://datalabs.inc42.com — Auth0 signup | logged-out | page ¦ device |  | Yes |  | web ¦ backend | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | New user registration | Confirmed correct | 2026-08-29 | Difficult to track, Auth0 dependency ¦ PostHog: Y - 6695 (90d) ¦ Customer.io: Y (57% of profiles) ¦ No action
user_engagement | Login | Login | datalabs | User Login ¦ event `Login` fires | https://datalabs.inc42.com — Auth0 login | any | page ¦ device |  | Yes |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | Inc42 login success | Confirmed correct | 2026-08-29 | PostHog: Y - 15654 (90d) ¦ Customer.io: Y (60% of profiles) ¦ No action
monetization | Pro Trial | Pro Trial | datalabs | User's pro trial begins ¦ event `Pro Trial` fires | https://datalabs.inc42.com — trial / checkout start | logged-in | page ¦ device | Trial Type Trial Stage event_id = pro_trial event_name = pro_trial event_time in GMT fbp | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | manual | Own GTM + PostHog project 66351 — verify there, not Media | User's pro trial begins | Confirmed correct | 2026-08-29 | PostHog: Y - 305 (90d) ¦ Customer.io: Y (13% of profiles; used in 1 broadcast + 3 automations) ¦ No action
user_engagement | Lock Type Lock Interaction | Lock Type Lock Interaction | datalabs | User interacts with freewall lock on the platform ¦ event `Lock Type Lock Interaction` fires | https://datalabs.inc42.com | any | page ¦ device | Lock Type Button Interaction event_id = register_lock event_name = register_lock event_time in GMT fbp | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | User interacts with freewall lock on the platform
user_engagement | Logout | Logout | datalabs | User Logout ¦ event `Logout` fires | https://datalabs.inc42.com | any | page ¦ device |  | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | Manual logout on Inc42 account | Confirmed correct | 2026-08-29 | PostHog: Y - 365 (90d) ¦ Customer.io: Y (<1% of profiles) ¦ No action
page_view | Pageview | Pageview | datalabs | Open / navigate to the page ¦ page finishes loading ¦ event fires (Pageview) | https://datalabs.inc42.com — page load | any | page ¦ pro ¦ device | Model Device Type Browser OS | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When any page is viewed | Renamed (cosmetic) + volume anomaly | 2026-08-29 | PostHog: Y BUT CRITICAL: custom 'Page View' event only 7 occurrences in 90d - near-zero. PostHog's autocapture $pageview (552,088) is a SEPARATE built-in event, not this one - do not conflate ¦ Customer.io: Y (91% of profiles - highest-volume event in workspace) ¦ Live name: Page View ¦ Update sheet: production fires as "Page View" (two words, capitalized), sheet says "Pageview". SEPARATE ISSUE: the custom "Page View" event itself is nearly dead in PostHog (7 events in 90 days) vs 91% of Customer.io profiles - the vast majority of page-view tracking is going through PostHog's autocapture $pageview instead of this custom event. Needs product owner decision on whether the custom event is still needed.
user_engagement | Datalab Onboarding | Datalab Onboarding | datalabs | Click on "Get Started" on first screen of onboarding flow ¦ event `Datalab Onboarding` fires | https://datalabs.inc42.com — onboarding flow | logged-in | page ¦ interaction | Datalab Onboarding State | Yes |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user starts onboarding flow | Property mismatch | 2026-08-29 | PostHog: Y - 17581 (90d) ¦ Customer.io: Y (54% of profiles; used in 4 places) ¦ Update sheet to document the event_id/event_name/event_time/fbp/Login Method/User ID properties that are actually being sent alongside Datalab Onboarding State
search_action | Search Active | Search Active | datalabs | First click on global search bar ¦ event `Search Active` fires | https://datalabs.inc42.com — search / company search | any | page ¦ interaction | Search Type Search Source Search Content | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user clicks on search icon button/bar and search becomes active | Confirmed correct | 2026-08-29 | PostHog: Y - 9514 (90d) ¦ Customer.io: Y (15% of profiles) ¦ No action
search_action | Search Completed | Search Completed | datalabs | Search results generated & displayed ¦ event `Search Completed` fires | https://datalabs.inc42.com — search / company search | any | page ¦ interaction | Search Type Search Source Search Query | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | User clicks the search button or hits enter to perform the search | Confirmed correct | 2026-08-29 | PostHog: Y - 16252 (90d) ¦ Customer.io: Y (13% of profiles) ¦ No action
user_engagement | Advanced Filter Clicked | Advanced Filter Clicked | datalabs | Click on Advanced Filter button ¦ event `Advanced Filter Clicked` fires | https://datalabs.inc42.com — advanced filters | any | page ¦ interaction | Advanced Filter State Table View (new) | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user opens or closes advance filter bar | Confirmed correct | 2026-08-29 | PostHog: Y - 4522 (90d) ¦ Customer.io: Y (8% of profiles) ¦ No action
user_engagement | Advanced Filter Applied | Advanced Filter Applied | datalabs | Advanced Filteration Completed ¦ event `Advanced Filter Applied` fires | https://datalabs.inc42.com — advanced filters | any | page ¦ interaction | Filter Property Type Filter Property Value Table View (new) | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When a user clicks on apply filter button, based on type of filter selected | Confirmed correct | 2026-08-29 | PostHog: Y - 21904 (90d) ¦ Customer.io: Y (13% of profiles; used in 1 automation) ¦ No action
user_engagement | Customise Columns Applied | Customise Columns Applied | datalabs | Made changes in Customise column feature ¦ event `Customise Columns Applied` fires | https://datalabs.inc42.com | any | page ¦ interaction | Customise Column Properties | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When a user customise column order | Renamed - remark is stale | 2026-08-29 | Event name coming as "Customise Column Clicked", should be "Customise Column Applied" ¦ PostHog: Y - 523 (90d) as 'Customize Columns Applied' - CONFIRMS CIO finding exactly, same spelling both platforms ¦ Customer.io: Y (1% of profiles) ¦ Live name: Customize Columns Applied ¦ Update sheet: the documented bug ("fires as Customise Column Clicked") is NOT what's happening today. Actual live name is "Customize Columns Applied" - correct the remark and decide whether to standardize spelling to Customise (matches rest of property naming) or Customize
table_action | Table Sort | Table Sort | datalabs | Click on sort option in table ¦ event `Table Sort` fires | https://datalabs.inc42.com | any | page ¦ interaction | Table Name Table Sort Column Name Table Sort Order Table View (new) | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user sorts table by ascending/descending order | Both documented bugs appear FIXED; new minor property-name drift found | 2026-08-29 | 1. "Customise Column Properties" property also being triggered in this event 2. If doing sort action on company search table, "Table Name" is coming as "company", should be "company search" ¦ PostHog: Y - 2044 (90d) ¦ Customer.io: Y (4% of profiles) ¦ Update sheet: (1) mark both existing remarks as resolved/re-verify with a larger sample, (2) correct property name from "Table Sort Order" to "Table Sort Orderby"
user_engagement | Table Pagination | Table Pagination | datalabs | Click next/previous page ¦ event `Table Pagination` fires | https://datalabs.inc42.com | any | page | Table Name Pagination Page Number Table View (new) | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user view more pages of same table | Confirmed correct | 2026-08-29 | PostHog: Y - 59005 (90d) - highest-volume custom event ¦ Customer.io: Y (9% of profiles) ¦ No action
feedback_action | Form Submitted | Form Submitted | datalabs | User submits feedback form ¦ event `Form Submitted` fires | https://datalabs.inc42.com | any | page ¦ interaction | Form Type | Yes |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When a user completes form submission | Confirmed correct | 2026-08-29 | PostHog: Y - 676 (90d) ¦ Customer.io: Y (5% of profiles) ¦ No action
user_engagement | Tab View (Rename to Section Interaction in future) | Tab View (Rename to Section Interaction in future) | datalabs | Click perform any action on section in a page ¦ event `Tab View (Rename to Section Interaction in future)` fires | https://datalabs.inc42.com | any | page ¦ interaction ¦ content | Section Name Tab Name Data Visualisation Metric Type Chart Type Date Range | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user interacts with different tabs on profile sub-sections |  |  | Tab view event is designed for Tables inside the tab, eg. "Funding amount over time" is a tab under funding table in Funding Tab
user_engagement | Edit Interaction | Edit Interaction | datalabs | User performs edit action in profile/list/saved search ¦ event `Edit Interaction` fires | https://datalabs.inc42.com | any | page ¦ interaction | Edit Type Edit Field Edit Source Edit Status Edit Item ID | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user performs any edit action inside profile/list/saved search besides delete action | Confirmed correct | 2026-08-29 | PostHog: Y - 696 (90d) ¦ Customer.io: Y (3% of profiles) ¦ No action
user_engagement | Checkbox Interaction | Checkbox Interaction | datalabs | User performs any interaction on checkbox ¦ event `Checkbox Interaction` fires | https://datalabs.inc42.com | any | page ¦ interaction | Checkbox Type Data Type Selection Source Selection Status | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user performs any interaction on checkbox be it on any page like search page, list page or saved search page | Confirmed correct | 2026-08-29 | PostHog: Y - 1531 (90d) ¦ Customer.io: Y (2% of profiles) ¦ No action
user_engagement | List Interaction | List Interaction | datalabs | User performs any action in list ¦ event `List Interaction` fires | https://datalabs.inc42.com | any | page ¦ interaction | List Interaction Type List Interaction Source List ID List Type | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user performs any interaction in list, be it creation, addition, deletion from any source on platform | Confirmed correct | 2026-08-29 | PostHog: Y - 1545 (90d) ¦ Customer.io: Y (3% of profiles) ¦ No action
user_engagement | Alert Interaction | Alert Interaction | datalabs | User performs any action on alerts ¦ event `Alert Interaction` fires | https://datalabs.inc42.com | any | page ¦ interaction | Alert Type Alert Status Alert Content User : industry_alert_subscribed | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user performs any interaction related to alerts, be it enabling, disabling, changing frequency or delivery method of alert. | Confirmed correct | 2026-08-29 | PostHog: Y - 5141 (90d) ¦ Customer.io: Y (49% of profiles) ¦ No action
user_engagement | Click Interaction | Click Interaction | datalabs | User interacts with any button on the platform ¦ event `Click Interaction` fires | https://datalabs.inc42.com | any | page ¦ interaction | Button Type Button Interaction Button Content | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user interacts with any button on the platform | Confirmed correct | 2026-08-29 | PostHog: Y - 6977 (90d) ¦ Customer.io: Y (15% of profiles) ¦ No action
user_engagement | Scroll Depth | Scroll Depth | datalabs | User scrolls on any page on Datalabs ¦ event `Scroll Depth` fires | https://datalabs.inc42.com | any | page | Scroll Percentage | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When a user starts scrolling on any page. | Partially firing - PostHog only, renamed, negligible volume | 2026-08-29 | PostHog: Y BUT as lowercase 'scroll_depth' (different naming), only 2 events total, first_seen 2026-08-12 - brand new and negligible volume, not the broken event CIO shows ¦ Customer.io: N - zero matches in Customer.io's 39 live events ¦ Live name: N/A ¦ Needs product owner decision. Live in PostHog as lowercase 'scroll_depth' (not 'Scroll Depth'), only 2 events since 2026-08-12 - looks like a fresh/incomplete rollout, not simply broken. Not reaching Customer.io at all yet. Confirm rollout status with engineering before treating as the same 'Paused' item noted in the 27-Aug tracking review.
user_engagement | Custom Filter Applied | Custom Filter Applied | datalabs | User selects specific dropdown and filters from subtabs of a profile page ¦ event `Custom Filter Applied` fires | https://datalabs.inc42.com — advanced filters | any | page | Section Name, Filter Type, Filter Value | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user selects specific filters in profile pages | Broken - not firing | 2026-08-29 | PostHog: N - zero matches in PostHog 90d event list either ¦ Customer.io: N - zero matches in Customer.io's 39 live events ¦ Live name: N/A ¦ Needs product owner decision
user_engagement | Demo Call | Demo Call | datalabs | Demo Call button click on site ¦ event `Demo Call` fires | https://datalabs.inc42.com | any | page ¦ device | Booking Stage Modal Name Modal Type | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user clicks on demo call button and is taken to a page where form needs to be filled | Platform gap - fires to Customer.io, not to PostHog | 2026-08-29 | PostHog: N - zero matches in PostHog 90d event list (differs from CIO, which shows <1%) - platform-specific gap ¦ Customer.io: Y (<1% of profiles) ¦ Needs engineering investigation: fires to Customer.io (<1% of profiles) but has zero occurrences in PostHog's 90-day event list. Confirm whether the PostHog SDK call was ever wired for this event.
user_engagement | Demo Call Booked | Demo Call Booked | datalabs | Demo Call Booked ¦ event `Demo Call Booked` fires | https://datalabs.inc42.com | any |  | event_id event_time fbp | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When a user books demo call after filling information and choosing time slot | Platform gap - fires to Customer.io, not to PostHog | 2026-08-29 | PostHog: N - zero matches in PostHog 90d event list (differs from CIO, which shows <1%) - platform-specific gap ¦ Customer.io: Y (<1% of profiles) ¦ Needs engineering investigation: fires to Customer.io (<1% of profiles) but has zero occurrences in PostHog's 90-day event list. Confirm whether the PostHog SDK call was ever wired for this event.
monetization | Cancel Plus Membership | Cancel Plus Membership | datalabs | When user intends to cancel plus membership ¦ event `Cancel Plus Membership` fires | https://datalabs.inc42.com | logged-in | page ¦ interaction | Plus Cancellation State | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user intends to cancel plus membership | Broken - not firing | 2026-08-29 | PostHog: N - zero matches in PostHog 90d event list either ¦ Customer.io: N - zero matches in Customer.io's 39 live events (no ""cancel"" event of any kind exists) ¦ Live name: N/A ¦ Needs product owner decision / fix production. Also see New Events Found tab: a "Plus Subscribed" event exists in Customer.io with no matching sheet row at all - the subscribe side is live but undocumented while the cancel side is documented but not firing
monetization | Pro Lock Interaction | Pro Lock Interaction | datalabs | Whenever a user interacts with features behind pro lock ¦ event `Pro Lock Interaction` fires | https://datalabs.inc42.com | logged-in | page ¦ interaction | Modal Type Modal Name | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | manual | Own GTM + PostHog project 66351 — verify there, not Media | When user intends to cancel Datalabs Pro membership | Confirmed correct | 2026-08-29 | PostHog: Y - 1930 (90d) ¦ Customer.io: Y (10% of profiles) ¦ No action
monetization | Pro Payment | Pro Payment | datalabs | When user has initiated to buy Datalabs Pro membership ¦ event `Pro Payment` fires | https://datalabs.inc42.com — Razorpay checkout | logged-in | page ¦ interaction | Payment Stage Pro Membership Type | No |  | backend | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | manual | Own GTM + PostHog project 66351 — verify there, not Media | When user intends to cancel Datalabs Pro membership | Confirmed correct | 2026-08-29 | PostHog: Y - 2161 (90d) ¦ Customer.io: Y (5% of profiles; used in 1 automation) ¦ No action
monetization | Cancel Pro Membership | Cancel Pro Membership | datalabs | When user intends to cancel Datalabs Pro membership ¦ event `Cancel Pro Membership` fires | https://datalabs.inc42.com | logged-in | page ¦ interaction ¦ pro | Pro Cancellation State Pro Membership Type | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | manual | Own GTM + PostHog project 66351 — verify there, not Media | When user intends to cancel Datalabs Pro membership | Broken - not firing | 2026-08-29 | PostHog: N - zero matches in PostHog 90d event list either ¦ Customer.io: N - zero matches in Customer.io's 39 live events ¦ Live name: N/A ¦ Needs product owner decision
search_action | AI Search Active | AI Search Active | datalabs | When user clicks on search box to type prompt ¦ event `AI Search Active` fires | https://datalabs.inc42.com — search / company search | any | page ¦ interaction | Search Type | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user clicks on search box to type prompt | Confirmed correct | 2026-08-29 | PostHog: Y - 2592 (90d) ¦ Customer.io: Y (4% of profiles) ¦ No action
search_action | AI Search Completed | AI Search Completed | datalabs | When user submits prompt in search box ¦ event `AI Search Completed` fires | https://datalabs.inc42.com — search / company search | any | page ¦ interaction | Search Type Prompt Type | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user submits prompt in search box | Confirmed correct | 2026-08-29 | PostHog: Y - 1859 (90d) ¦ Customer.io: Y (4% of profiles) ¦ No action
user_engagement | Ask Feedback | Ask Feedback | datalabs | When user submits feedback on any response ¦ event `Ask Feedback` fires | https://datalabs.inc42.com — Ask / AI | any | page ¦ interaction | Response Feedback | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user submits feedback on any response | Confirmed correct | 2026-08-29 | PostHog: Y - 35 (90d) ¦ Customer.io: Y (<1% of profiles) ¦ No action
user_engagement | Ask Interaction | Ask Interaction | datalabs | When user clicks on any link generated by AI agent ¦ event `Ask Interaction` fires | https://datalabs.inc42.com — Ask / AI | any | page ¦ interaction | Interaction Type : {Click} Click Type : {Source Button, Source Link, Copy, New Chat} | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user clicks on any link generated by AI agent | Confirmed correct | 2026-08-29 | PostHog: Y - 207 (90d) ¦ Customer.io: Y (<1% of profiles) ¦ No action
user_engagement | Limit Reached | Limit Reached | datalabs | When a user hits their daily prompt limit ¦ event `Limit Reached` fires | https://datalabs.inc42.com | any | page ¦ interaction | Not individually inspected beyond name match | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user clicks on any link generated by AI agent | Confirmed correct | 2026-08-29 | PostHog: Y - 13 (90d) ¦ Customer.io: Y (<1% of profiles) ¦ No action
search_action | Saved Search Interaction | Saved Search Interaction | datalabs | User performs any action in saved search ¦ event `Saved Search Interaction` fires | https://datalabs.inc42.com — search / company search | logged-in | page ¦ interaction | Saved Search Type Saved Search Interaction Type Search Search Source Saved Search ID | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user performs any interaction in saved search, be it creation, updation or deletion from any source on platform | Confirmed correct | 2026-08-29 | PostHog: Y - 625 (90d) ¦ Customer.io: Y (2% of profiles) ¦ No action
sidebar | Sidebar Interaction | Sidebar Interaction | datalabs | User performs any action in sidebar on desktop ¦ event `Sidebar Interaction` fires | https://datalabs.inc42.com | any | page ¦ interaction | Set Sidebar State | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user performs any interaction on sidebar | Confirmed correct | 2026-08-29 | PostHog: Y - 1413 (90d) ¦ Customer.io: Y (4% of profiles) ¦ No action
report | Report Interaction | Report Interaction | datalabs | User performs any interaction on published reports ¦ event `Report Interaction` fires | https://datalabs.inc42.com | any | page ¦ interaction | Access Type Access URL Report Name | No |  | web ¦ backend | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user performs any interaction on published reports on platform | Confirmed correct | 2026-08-29 | PostHog: Y - 3767 (90d) ¦ Customer.io: Y (22% of profiles) ¦ No action
data_verification | Data Verification | Data Verification | datalabs | User performs any interaction on verification flows ¦ event `Data Verification` fires | https://datalabs.inc42.com | any | page ¦ interaction | Verification Stage Verification Type | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user performs any interaction on verification flows on platform | Broken - not firing | 2026-08-29 | PostHog: N - zero matches in PostHog 90d event list either ¦ Customer.io: N - zero matches in Customer.io's 39 live events ¦ Live name: N/A ¦ Needs product owner decision
my_feed | Feed Interaction | Feed Interaction | datalabs | User performs any interaction on feed ¦ event `Feed Interaction` fires | https://datalabs.inc42.com | any | page ¦ interaction | Feed Filter Type Feed Filter Value | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user performs any interaction on feed | Confirmed correct | 2026-08-29 | PostHog: Y - 585 (90d) ¦ Customer.io: Y (1% of profiles) ¦ No action
user_engagement | Post Interaction | Post Interaction | datalabs | User performs any interaction on the post ¦ event `Post Interaction` fires | https://datalabs.inc42.com | any | page ¦ interaction | Post ID Button Type Button Interaction Button Content | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user performs any interaction on post | Confirmed correct | 2026-08-29 | PostHog: Y - 44 (90d) ¦ Customer.io: Y (<1% of profiles) ¦ No action
monetization | Credit Payment | Credit Payment | datalabs | User initiates the flow to purchase addional credits ¦ event `Credit Payment` fires | https://datalabs.inc42.com — Razorpay checkout | logged-in | page ¦ interaction | Credit Payment Stage Credit Topup Plan | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | manual | Own GTM + PostHog project 66351 — verify there, not Media | When user performs any interaction to purchse addional credits | Confirmed correct | 2026-08-29 | PostHog: Y - 58 (90d) ¦ Customer.io: Y (<1% of profiles) ¦ No action
export_data | Export Interaction | Export Interaction | datalabs | User performs any interaction on export feature on platform ¦ event `Export Interaction` fires | https://datalabs.inc42.com | any | page ¦ interaction | Data Type Export Stage Export Type File Format Profiles Exported | No |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | When user performs any interaction on the export feature | Confirmed correct | 2026-08-29 | PostHog: Y - 414 (90d) ¦ Customer.io: Y (2% of profiles) ¦ No action
monetization | pro_subscription | pro_subscription | datalabs | ACCESS state changed. One event, stage carries the meaning. Backend only. ¦ event `pro_subscription` fires | https://datalabs.inc42.com | any | lifecycle envelope ¦ subscription | subscription_stage trial_end_at current_period_end_at next_charge_amount renewal_count mandate_status | No |  | web ¦ backend | customerio ¦ posthog ¦ cio | manual | Own GTM + PostHog project 66351 — verify there, not Media | Fires on every Datalabs Pro subscription state change, expressed as a business meaning rather than a WooCommerce status. | Descoped | 2026-08-29 | NO ads destinations — a failed renewal must never fire a Meta/Google conversion. Replaces the state-check "Trial Started" automation. See datalabs-pro-instrumentation-spec-2026-08.md §2.1 for per-stage derivation rules. CAMPAIGN BUILD WARNING: never branch on a bare CIO `Event` condition for this event — it has no attribute filter, so "performed pro_subscription" is true for ANY stage. Branch on profile attributes or a segment (spec §3.6). ¦ PostHog: DESCOPED - out of scope for this audit per explicit instruction ¦ Customer.io: DESCOPED ¦ Live name: DESCOPED ¦ Not covered by this audit - descoped
monetization | pro_billing | pro_billing | datalabs | MONEY moved, or failed to. Backend only. ¦ event `pro_billing` fires | https://datalabs.inc42.com | any | lifecycle envelope ¦ billing | billing_stage order_id order_type amount renewal_count failure_reason | No |  | web ¦ backend | customerio ¦ posthog ¦ cio | manual | Own GTM + PostHog project 66351 — verify there, not Media | Fires on every Datalabs Pro payment outcome: purchase, first charge, renewal, failure, abandoned checkout, refund. | Descoped | 2026-08-29 | NO ads destinations — a failed renewal must never fire a Meta/Google conversion. Distinct from the existing frontend `Pro Payment` funnel event, which stays as-is for ads/CAPI. See spec §2.2. CAMPAIGN BUILD WARNING: a bare CIO `Event` condition ("performed pro_billing") is TRUE for renewal_failed as well as renewal_succeeded — it cannot tell success from failure. Exit the grace sequence on pro_subscription_status != past_due, never on the event (spec §3.6). ¦ PostHog: DESCOPED - out of scope for this audit per explicit instruction ¦ Customer.io: DESCOPED ¦ Live name: DESCOPED ¦ Not covered by this audit - descoped
user_engagement | user_registered | user_registered | datalabs | Open signup ¦ complete Auth0 registration ¦ land authenticated | https://datalabs.inc42.com — Auth0 signup | logged-out | page ¦ device | register_source entry_page_type registration_page_url | Yes |  | web ¦ backend | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | Unchanged behaviour. Adds the two properties Journey A/B/C assignment needs. | Broken - not firing (planned rename not yet shipped) | 2026-08-29 | entry_page_type MUST also persist as a user property — today DL Page Type is event-only, which is why Journey B-vs-C cannot be evaluated at enrollment. ¦ PostHog: N - not present under this name; only old 'Registered' fires (6695 in 90d) ¦ Customer.io: N - not present in Customer.io under this name; the old ""Registered"" event is still what fires ¦ Live name: N/A (renamed event not yet live) ¦ Needs product owner decision - confirm rollout timeline for the user_registered rename before treating sheet as describing current production
user_engagement | onboarding_lifecycle | onboarding_lifecycle | datalabs | Onboarding progress (existing `Datalab Onboarding`, renamed) ¦ event `onboarding_lifecycle` fires | https://datalabs.inc42.com — onboarding flow | logged-in | page | onboarding_stage | Yes |  | web | customerio ¦ posthog ¦ mixpanel ¦ ga4 ¦ moengage ¦ meta ¦ google_ads ¦ linkedin ¦ userguiding | auto | Own GTM + PostHog project 66351 — verify there, not Media | Unchanged behaviour. Enum gains step_1. | Broken - not firing (planned rename not yet shipped); completion-sync claim PARTIALLY confirmed | 2026-08-29 | Current enum starts at "Onboarding Step 2" — first-step drop-off is unmeasurable. Also: datalabs_onboarding_complete is 99% populated in PostHog but 66% broken in CIO — the SYNC is the bug, not the field (Bhavika, User Properties ¦ New row 35). ¦ PostHog: N - not present under this name; only old 'Datalab Onboarding' fires. Completion flag cross-check: of 5,082 unique persons who fired 'Onboarding Completed' state (90d), 5,033 (99.03%) have 'Datalabs Onboarding Complete'=Yes as a PostHog person property - MATCHES sheet's claimed 99% in PostHog exactly ¦ Customer.io: N - not present under this name; old 'Datalab Onboarding' event still fires. Related attribute 'Datalabs Onboarding Complete' exists and covers 68% of all profiles (12439 of ~18293) - this is a different metric (attribute coverage) than the sheet's claimed 66% CIO-vs-PostHog completion mismatch and does not confirm or refute that specific figure ¦ Live name: N/A (renamed event not yet live) ¦ Needs product owner decision on rollout timeline for the rename. Completion-flag cross-check done: PostHog confirms 99.03% (5,033 of 5,082 completers) have the flag set - matches the sheet's '99% in PostHog' claim exactly. Customer.io side could not be precisely isolated to the same completer cohort this run (segment builder UI issue) - only a weaker figure is available (68% of ALL profiles, not scoped to completers, have the attribute set at all) - directionally consistent with a sync gap but not a confirmed 66%. Re-run the CIO-side cross-check to get an exact figure.
colour_code | Feature | Feature | datalabs |  | https://datalabs.inc42.com | any |  |  | No |  | web |  | auto | Own GTM + PostHog project 66351 — verify there, not Media
monetization | Live Properties | Live Properties | datalabs |  | https://datalabs.inc42.com | any |  |  | No |  | web |  | manual | Own GTM + PostHog project 66351 — verify there, not Media
abcdefg | Backlog | Backlog | datalabs |  | https://datalabs.inc42.com | any |  |  | No |  | web |  | auto | Own GTM + PostHog project 66351 — verify there, not Media
search_action | People Search | People Search | datalabs | Open search ¦ enter query ¦ submit / press Enter | https://datalabs.inc42.com — search / company search | any |  |  | No |  | web |  | auto | Own GTM + PostHog project 66351 — verify there, not Media
abcdefg | Captable | Captable | datalabs |  | https://datalabs.inc42.com | any |  |  | No |  | web |  | auto | Own GTM + PostHog project 66351 — verify there, not Media
user_engagement | Login Modal | Login Modal | datalabs | Open login ¦ complete auth ¦ session established | https://datalabs.inc42.com — Auth0 login | any |  | 4 event attributes captured on Customer.io (not individually inspected - event is dormant on both platforms) | No |  | web | customerio ¦ posthog ¦ first_seen_jul_29_2026_-_date_order_between_platforms_is_inconsistent ¦ worth_a_second_look) | auto | Own GTM + PostHog project 66351 — verify there, not Media | No action - appears to be an abandoned test/legacy event on both platforms; confirm with engineering it is not still wired anywhere before deleting | Dead-test event | 2026-08-29 | Volume: 0 in last 30 days on either platform
monetization | Plus Subscribed | Plus Subscribed | datalabs |  | https://datalabs.inc42.com — subscribe / plan UI | any |  | 34 event attributes captured on Customer.io (rich payload, not individually inspected) | No |  | web | customerio ¦ posthog ¦ first_seen_2026-06-02) | auto | Own GTM + PostHog project 66351 — verify there, not Media | Update sheet to add a row for this event - it is the Plus-membership subscribe/confirmation counterpart to the sheet's documented "Cancel Plus Membership" event, which itself is not firing at all (see main Audit tab). Live on both platforms with real volume. | Confirmed correct but undocumented | 2026-08-29 | Volume: 0 in last 30 days on either platform (recent 90-day activity on PostHog only)
user_engagement | master_agent_query | master_agent_query | datalabs |  | https://datalabs.inc42.com | any |  | Rich backend payload: query, query_type (discovery/company/sector/funding/people/ranking/comparison/investor/advisory/out_of_scope), mode (thinking/fast/deep_research), complexity, elapsed_ms, tool_co | No |  | web | posthog | auto | Own GTM + PostHog project 66351 — verify there, not Media | Add to sheet under Ask Datalabs category. This is the backend query-classification/orchestration event behind the AI Search / Ask Datalabs feature - it carries response-quality signals (evidence_density, ungrounded_claims) that look directly relevant to answer-quality monitoring and are not captured anywhere else in the documented event set. Needs product owner review to decide what should be formally tracked from this payload. | Confirmed correct but completely undocumented - high priority | 2026-08-29 | Volume: 2359 events in 90 days (high volume - largest undocumented event found)
Note on E1: HOW it fires: user/system steps, pipe-separated (Ashish sample style)
Note on F1: WHERE it fires: URL or app screen/component

## App
event_group | event_name | display_name | property | trigger_steps | trigger_url | login_state | event_property_groups | custom_event_properties | trigger_identify_call | expected_traits | source | destinations | automatable | test_notes | description | audit_status | audit_date | audit_notes
lifecycle | app_opened | app_opened | app | Launch or foreground the app ¦ new session starts ¦ event fires | App — cold/warm start (foreground) | n/a | super | source (organic/push/deeplink/banner) ¦ push_type (if push) | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Session baseline | Working | 2026-08-29 | PostHog: Y (3,696 in 90d) ¦ Customer.io: Y (72% of profiles) ¦ No known issue; confirmed live in PostHog ¦ Build: Not started
lifecycle | deep_link_opened | deep_link_opened | app | Universal/deep link resolved ¦ event `deep_link_opened` fires | App — deep link / universal link open | n/a | super | link_url ¦ destination_screen ¦ campaign utm_source utm_medium utm_content | No |  | ios ¦ android | posthog ¦ singular | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Channel attribution (QR, banner, email) | no source, medium, content | 2026-08-29 | PostHog: Y (1,026 in 90d) ¦ Customer.io: Y (28% of profiles) ¦ still broken — source/medium/content not captured, confirmed live 2026-08-29 ¦ Build: Not started ¦ Status: no source, medium, content
lifecycle | app_installed | app_installed | app | First app open after a fresh install (once per install) ¦ event `app_installed` fires | App — first install / install attribution path | n/a | super | no new properties (SDK captures platform ¦ os_version ¦ app_version ¦ device_model ¦ manufacturer) | Yes |  | ios ¦ android | posthog ¦ firebase ¦ customerio ¦ singular | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | First app open after a fresh install (once per install) | set properties call does not send these person properties, and are later updarted via identity call | 2026-08-29 | PostHog: Y (738 in 90d) ¦ Customer.io: Y (51% of profiles) ¦ No known issue; confirmed live ¦ Status: set properties call does not send these person properties, and are later updarted via identity call
lifecycle | app_updated | app_updated | app | First app open after an app-version update (version changed vs previous) ¦ event `app_updated` fires | App — native screen (see trigger_steps) | any | super | update_type (forced / voluntary) ¦ previous_version + version auto-captured by PostHog | No |  | ios ¦ android | posthog ¦ firebase ¦ customerio | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | First app open after an app-version update (version changed vs previous) | - | 2026-08-29 | PostHog: Y (38 in 90d) ¦ Customer.io: Y (2% of profiles) ¦ No known issue flagged; confirmed live, low volume ¦ Status: -
lifecycle | force_update_shown | force_update_shown | app | Min-version gate blocks entry ¦ event `force_update_shown` fires | App — native screen (see trigger_steps) | any | super | current_version ¦ min_version | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Ops — update-gate reach | - | 2026-08-29 | PostHog: N (0 in 90d) ¦ Customer.io: N (not expected in CIO per sheet) ¦ Not firing in 90-day window (may be rare — min-version gate rarely triggers) ¦ Build: Not started ¦ Status: -
user_engagement | onboarding | onboarding | app | Flow state machine (consolidated per web convention — like Plus Onboarding State) ¦ event `onboarding` fires | App — onboarding | logged-in | super | status (started/step_completed/step_skipped) · step_name (role/sectors/topic/push_prompt/signin_prompt) · step_number · selection_count · step_answer (role: enum · sectors/topic: array · prompts: outcome) | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Onboarding funnel (property-filtered steps) | Working | 2026-08-29 | PostHog: Y (4,301 in 90d) ¦ Customer.io: Y (61% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
user_engagement | onboarding_completed | onboarding_completed | app | Final step done — STANDALONE (name-keyed destinations) ¦ event `onboarding_completed` fires | App — onboarding | logged-in | super | role ¦ sector_groups (7-group array) ¦ topic_groups | Yes |  | ios ¦ android | posthog ¦ firebase ¦ customerio ¦ singular | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Onboarding completion; UAC signal | Working | 2026-08-29 | PostHog: Y (940 in 90d) ¦ Customer.io: Y (49% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
onboarding | walkthrough | walkthrough | app | User taps Next / Skip / Done on a virtual-tour stop (state machine; 3 stops) ¦ event `walkthrough` fires | App — native screen (see trigger_steps) | any | super | status (next / skip_tour / done) ¦ step_name (brief / explore / watchlist) ¦ step_number (1–3) | Yes |  | ios ¦ android | posthog ¦ customerio | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | User taps Next / Skip / Done on a virtual-tour stop (state machine; 3 stops) | Working | 2026-08-29 | PostHog: Y (2,040 in 90d) ¦ Customer.io: Y (41% of profiles) ¦ No known issue; confirmed live
brief | brief_page_opened | brief_page_opened | app | Brief home page opened, or edition day switched via the date strip ¦ event `brief_page_opened` fires | App — Brief tab / brief cards | n/a | super | source (organic / brief/ explore/ watchlist/ deeplink / push) ¦ edition_date ¦ is_today edition_type | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Brief home page opened, or edition day switched via the date strip | source is still wrong | 2026-08-29 | PostHog: Y (8,535 in 90d) ¦ Customer.io: Y (60% of profiles) ¦ appears FIXED (no longer null/blank) — recommend product owner spot-check values are semantically correct ¦ Status: source is still wrong
brief | brief_opened | brief_opened | app | Cover CTA tapped → first card ¦ event `brief_opened` fires | App — Brief tab / brief cards | n/a | super | edition_date ¦ story_count ¦ source (push/organic/deeplink) ¦ is_first_brief edition_type | No |  | ios ¦ android | posthog ¦ firebase ¦ customerio ¦ singular | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Retention basis event; completion-rate denominator | Working | 2026-08-29 | PostHog: Y (2,579 in 90d) ¦ Customer.io: Y (34% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
brief | card_viewed | card_viewed | app | Card enters viewport ¦ event `card_viewed` fires | App — native screen (see trigger_steps) | any | super + story | edition_date ¦ position ¦ card_type (editorial/signal/recap) ¦ story_id ¦ is_boosted ¦ boost_reason (featured/tracked_company/tracked_sector/none) edition_type | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Card drop-off curve; boost effectiveness; editorial feedback loop | Working | 2026-08-29 | PostHog: Y (13,164 in 90d) ¦ Customer.io: Y (33% of profiles) ¦ No known issue; confirmed live — highest volume event as expected ¦ Build: Not started
brief | article_opened | article_opened | app | Full article opened from card/list ¦ event `article_opened` fires | App — in-article screen | n/a | super + story | story_id ¦ source (brief_card/article_reader/company_page/watchlist/explore/search/push/profile/deeplink) ¦ position | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Brief → article depth; boost honesty check | Working | 2026-08-29 | PostHog: Y (1,903 in 90d) ¦ Customer.io: Y (29% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
brief | decode | decode | app | Decode (live AI explainer) state machine (consolidated) ¦ event `decode` fires | App — native screen (see trigger_steps) | any | super + story | status (requested/completed) · story_id · source (brief_card/explore/profile) · on completed: latency_ms · success | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Decode adoption + latency p50/p95 + failure rate | - | 2026-08-29 | PostHog: N (0 — event not found in PostHog taxonomy at all) ¦ Customer.io: N (not expected in CIO per sheet) ¦ STILL BROKEN — zero PostHog telemetry confirmed live 2026-08-29, matches prior review finding ¦ Build: Not started ¦ Status: -
brief | brief_completed | brief_completed | app | FINAL CARD REACHED — the canonical completion definition ¦ event `brief_completed` fires | App — Brief tab / brief cards | any | super | edition_date ¦ cards_viewed ¦ duration_sec edition_type | Yes |  | ios ¦ android | posthog ¦ firebase ¦ customerio ¦ singular | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | NORTH STAR; streak credit; §12 metric; Meta AEO optimization event | no setPersonProperties call | 2026-08-29 | PostHog: Y (953 in 90d) ¦ Customer.io: Y (16% of profiles) ¦ Status unresolved — property-level not re-verified ¦ Build: Not started ¦ Status: no setPersonProperties call
brief | brief_fallback_shown | brief_fallback_shown | app | Content-scarcity fallback (fewer cards + recap) ¦ event `brief_fallback_shown` fires | App — Brief tab / brief cards | any | super | reason (scarcity) ¦ card_count edition_type | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Ops — slow-day frequency | - | 2026-08-29 | PostHog: N (0 in 90d) ¦ Customer.io: N (not expected in CIO per sheet) ¦ Not firing in 90-day window — may be correctly rare (scarcity is infrequent) ¦ Build: Not started ¦ Status: -
brief | story_saved | story_saved | app | Save action ¦ event `story_saved` fires | App — story / article card or detail | logged-in | super + story | story_id ¦ source | Yes |  | ios ¦ android | posthog ¦ customerio | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Saved sub-tab usage | no setPersonProperties call | 2026-08-29 | PostHog: Y (270 in 90d) ¦ Customer.io: Y (5% of profiles) ¦ Status unresolved — property-level not re-verified ¦ Build: Not started ¦ Status: no setPersonProperties call
brief | story_unsaved | story_unsaved | app | Saved article removed from Saved ¦ event `story_unsaved` fires | App — story / article card or detail | logged-in | super + story | story_id ¦ source | Yes |  | ios ¦ android | posthog ¦ customerio | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Saved article removed from Saved | no setPersonProperties call | 2026-08-29 | PostHog: Y (66 in 90d) ¦ Customer.io: Y (1% of profiles) ¦ Status unresolved — property-level not re-verified ¦ Status: no setPersonProperties call
brief | story_shared | story_shared | app | Share sheet completed ¦ event `story_shared` fires | App — story / article card or detail | any | super + story | story_id ¦ channel ¦ source | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Organic loop signal | channel is wrong can keep only story_shared if chnnel can not be fetched | 2026-08-29 | PostHog: Y (93 in 90d) ¦ Customer.io: Y (4% of profiles) ¦ appears FIXED — channel now capturing real values ¦ Build: Not started ¦ Status: channel is wrong can keep only story_shared if chnnel can not be fetched
brief | card_rated | card_rated | app | User taps 👍 More like this / 👎 Less like this on a story card ¦ event `card_rated` fires | App — native screen (see trigger_steps) | any | super + story | edition_date ¦ rating (more_like_this / less_like_this) ¦ story_id ¦ position ¦ card_type (editorial/signal/recap) ¦ is_boosted ¦ boost_reason (featured/tracked_company/tracked_sector/none) edition_type | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | User taps 👍 More like this / 👎 Less like this on a story card | channel is wrong can keep only story_shared if chnnel can not be fetched | 2026-08-29 | PostHog: N (0 — event no longer fires under this name) ¦ Customer.io: N (not expected in CIO per sheet) ¦ RENAMED + still broken — brief_story_rated fires but channel is still null ¦ Build: Not started ¦ Status: channel is wrong can keep only story_shared if chnnel can not be fetched
streak | streak_opened | streak_opened | app | Streak screen opened by user tap ¦ event `streak_opened` fires | App — streak | n/a | super | source (profile/ brief/ explore/ watchlist) | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Streak screen opened by user tap | Working | 2026-08-29 | PostHog: Y (495 in 90d) ¦ Customer.io: Y (9% of profiles) ¦ No known issue; confirmed live
streak | streak_milestone_viewed | streak_milestone_viewed | app | Full-screen milestone (Day 1/7/30/100 only) ¦ event `streak_milestone_viewed` fires | App — streak | any | super | milestone_day ¦ tier (reader/regular/insider/ecosystem_native) ¦ is_refire | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Milestone reach; rating-prompt trigger | wrong, firing on nurelated days | 2026-08-29 | PostHog: Y (158 in 90d) ¦ Customer.io: Y (8% of profiles) ¦ still broken (circumstantial) — day_1 volume pattern looks too frequent for a one-time achievement; needs per-user trigger review ¦ Build: Not started ¦ Status: wrong, firing on nurelated days
user_engagement | watchlist_entity_added | watchlist_entity_added | app | Company/sector tracked ¦ event `watchlist_entity_added` fires | App — watchlist | logged-in | super | entity_type (company/sector) ¦ entity_id ¦ entity_name ¦ source (onboarding/article_reader/profile/explore/search/sector_landing) ¦ watchlist_size_before | Yes |  | ios ¦ android | posthog ¦ customerio ¦ singular | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Watchlist depth; digest eligibility | no setPersonProperties call..entity_name is null for sector..not null while removing it...watchlist_size_after is wrong | 2026-08-29 | PostHog: Y (307 in 90d) ¦ Customer.io: Y (5% of profiles) ¦ PARTIALLY FIXED — entity_name-for-sector now populates (fixed ~Aug 8); watchlist_size_after still broken; setPersonProperties still broken ¦ Build: Not started ¦ Status: no setPersonProperties call..entity_name is null for sector..not null while removing it...watchlist_size_after is wrong
user_engagement | watchlist_entity_removed | watchlist_entity_removed | app | Untracked ¦ event `watchlist_entity_removed` fires | App — watchlist | logged-in | super | entity_type ¦ entity_id ¦ watchlist_size_before ¦ source ,entity_name | Yes |  | ios ¦ android | posthog ¦ customerio | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Churn on tracked entities | no setPersonProperties call | 2026-08-29 | PostHog: Y (125 in 90d) ¦ Customer.io: Y (2% of profiles) ¦ Status unresolved — property-level not re-verified ¦ Build: Not started ¦ Status: no setPersonProperties call
user_engagement | watchlist_viewed | watchlist_viewed | app | Watchlist tab opened ¦ event `watchlist_viewed` fires | App — watchlist | logged-in | super | sub_tab (tracking/saved) ¦ entity_tab (company/industry) ¦ tracked_count | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Tab engagement | Working | 2026-08-29 | PostHog: Y (3,155 in 90d) ¦ Customer.io: Y (42% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
user_engagement | watchlist_limit_hit | watchlist_limit_hit | app | Free cap reached (~15 companies / 5 sectors) ¦ event `watchlist_limit_hit` fires | App — watchlist | logged-in | super | entity_type ¦ cap | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | UPSELL SIGNAL — cap pressure |  | 2026-08-29 | PostHog: N (0 in 90d) ¦ Customer.io: N (not expected in CIO per sheet) ¦ Not firing — may be correctly rare (cap rarely hit) or broken; can't distinguish from volume alone ¦ Build: Not started
content | explore_viewed | explore_viewed | app | Explore tab or sub-nav change ¦ event `explore_viewed` fires | App — Explore / News feed | any | super | sub_tab (articles/companies) ¦ pill_or_slice (feed/industry; recently_funded/top_funded/by_stage/by_sector/most_tracked) ¦ applied_filters | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Explore navigation patterns | Working | 2026-08-29 | PostHog: Y (7,866 in 90d) ¦ Customer.io: Y (50% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
content | sector_landing_viewed | sector_landing_viewed | app | Industry tag → sector landing ¦ event `sector_landing_viewed` fires | App — native screen (see trigger_steps) | any | super | sector ¦ sub_tab (companies/articles) ¦ source (card_tag/explore/search) | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Sector-landing usage | Working | 2026-08-29 | PostHog: Y (412 in 90d) ¦ Customer.io: Y (4% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
search_action | search_initiated | search_initiated | app | Search bar focused (funnel top: initiated → performed → tapped) ¦ event `search_initiated` fires | App — search | any | super | search_scope (articles/companies) ¦ surface | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Search abandonment (initiated → performed) | Working | 2026-08-29 | PostHog: Y (315 in 90d) ¦ Customer.io: Y (7% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
search_action | search_performed | search_performed | app | Query submitted ¦ event `search_performed` fires | App — search | any | super | query (raw) ¦ search_scope (articles/companies) ¦ result_count | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Search quality (zero-result rate = result_count 0) | Working | 2026-08-29 | PostHog: Y (916 in 90d) ¦ Customer.io: Y (7% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
search_action | search_result_tapped | search_result_tapped | app | Result opened ¦ event `search_result_tapped` fires | App — search | any | super | query ¦ position ¦ result_type (article/company/sector) ¦ entity_or_story_id | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Search relevance (tap position) | entity_or_story_id contains story slug instead of id for artcile tapping | 2026-08-29 | PostHog: Y (246 in 90d) ¦ Customer.io: Y (5% of profiles) ¦ appears FIXED — no slug values seen in current sample ¦ Build: Not started ¦ Status: entity_or_story_id contains story slug instead of id for artcile tapping
profiles | company_profile_viewed | company_profile_viewed | app | Profile opened ¦ event `company_profile_viewed` fires | App — company profile / companies | any | super | company_id ¦ company_name ¦ source (watchlist/explore/search/article_reader/company_page/sector_landing/brief_card/deeplink) ¦ is_tracked | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Profile reach; Datalabs surface usage | Working | 2026-08-29 | PostHog: Y (723 in 90d) ¦ Customer.io: Y (12% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
profiles | profile_opened | profile_opened | app | User's Profile tab opened ¦ event `profile_opened` fires | App — profile tab | n/a | super | source(brief/explore/watchlist) | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | User's Profile tab opened | Working | 2026-08-29 | PostHog: Y (1,542 in 90d) ¦ Customer.io: Y (22% of profiles) ¦ No known issue; confirmed live
profiles | profile_section_viewed | profile_section_viewed | app | Section scrolled into view ¦ event `profile_section_viewed` fires | App — profile tab | any | super | section (funding/financial_overview/corporate_activity/key_people/recent_activity) | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Section-level depth (V2+ P&L validation) | Working | 2026-08-29 | PostHog: Y (2,823 in 90d) ¦ Customer.io: Y (11% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
profiles | locked_feature_tapped | locked_feature_tapped | app | 🔒 gated feature tapped ¦ event `locked_feature_tapped` fires | App — native screen (see trigger_steps) | any | super | feature (alerts/filters/exports/api/reporting) ¦ surface | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | UPSELL SIGNAL — feature appetite |  | 2026-08-29 | PostHog: N (0 in 90d) ¦ Customer.io: N (not expected in CIO per sheet) ¦ Not firing — feature/surface never triggers event in 90-day window ¦ Build: Not started
profiles | interest_captured | interest_captured | app | "Notify me when ready" submitted ¦ event `interest_captured` fires | App — native screen (see trigger_steps) | any | super | feature ¦ surface | Yes |  | ios ¦ android | posthog ¦ customerio | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | THE v1 monetization dataset (Plus/Pro waitlist) |  | 2026-08-29 | PostHog: N (0 in 90d — event does not exist in PostHog taxonomy either) ¦ Customer.io: N ¦ STILL BROKEN — absent from BOTH PostHog and Customer.io despite sheet marking both as expected (escalates prior CIO-only finding) ¦ Build: Not started
notifications | push_permission_prompted | push_permission_prompted | app | Pre-prompt or OS prompt shown ¦ event `push_permission_prompted` fires | App — push notification open | any | super | context (onboarding/post_first_brief) ¦ prompt_type (pre_prompt/os) | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Opt-in funnel denominator | Working | 2026-08-29 | PostHog: Y (994 in 90d) ¦ Customer.io: Y (52% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
notifications | push_permission_granted | push_permission_granted | app | OS grant ¦ event `push_permission_granted` fires | App — push notification open | any | super | context | Yes |  | ios ¦ android | posthog ¦ firebase ¦ customerio ¦ singular | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Push opt-in rate; retention signal | setPersonProperties call not working(non logged in user)..working for logged in user | 2026-08-29 | PostHog: Y (454 in 90d) ¦ Customer.io: Y (33% of profiles) ¦ still broken (circumstantial) — no app-level person property set visible in $set on any sample; logged-in vs anon split not distinguishable from this data ¦ Build: Not started ¦ Status: setPersonProperties call not working(non logged in user)..working for logged in user
notifications | push_permission_denied | push_permission_denied | app | OS deny ¦ event `push_permission_denied` fires | App — push notification open | any | super | context | Yes |  | ios ¦ android | posthog ¦ customerio | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Opt-in funnel; re-prompt eligibility | setPersonProperties call not working(non logged in user)..working for logged in user | 2026-08-29 | PostHog: Y (464 in 90d) ¦ Customer.io: Y (18% of profiles) ¦ still broken (circumstantial) — same as push_permission_granted ¦ Build: Not started ¦ Status: setPersonProperties call not working(non logged in user)..working for logged in user
notifications | push_delivered | push_delivered | app | CLIENT-SIDE delivery confirm (Android esp.) ¦ event `push_delivered` fires | App — push notification open | any | super | push_type ¦ message_id ¦ manufacturer | Yes |  | ios ¦ android | posthog ¦ customerio | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | OEM TRIP-WIRE (Launch Infra A3/D5): vs CIO send counts by manufacturer → MoEngage decision | - | 2026-08-29 | PostHog: N (0 — event not found in PostHog taxonomy at all) ¦ Customer.io: N ¦ STILL BROKEN — confirmed zero volume in PostHog live 2026-08-29 AND absent from Customer.io; matches prior review finding of never firing ¦ Build: Not started ¦ Status: -
notifications | push_opened | push_opened | app | Notification tapped ¦ event `push_opened` fires | App — push notification open | n/a | super | push_type (morning_brief/nudge/breaking/watchlist_digest/winback) ¦ message_id ¦ campaign ¦ variant | No |  | ios ¦ android | posthog ¦ customerio ¦ singular | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Push CTR; edition-line A/B readout | - | 2026-08-29 | PostHog: Y (2 total in 90d, BOTH on 2026-07-10; ZERO in last 30 days) ¦ Customer.io: Y (<1% of profiles) ¦ STILL BROKEN — only 2 lifetime events, none since mid-July, despite 67% push opt-in per prior review ¦ Build: Not started ¦ Status: -
notifications | notification_settings_changed | notification_settings_changed | app | Any push setting toggled ¦ event `notification_settings_changed` fires | App — native screen (see trigger_steps) | any | super | setting ¦ new_value | Yes |  | ios ¦ android | posthog ¦ customerio | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Fatigue signal; send eligibility | setPersonProperties call not working(non logged in user)..working for logged in user | 2026-08-29 | PostHog: Y (79 in 90d) ¦ Customer.io: Y (1% of profiles) ¦ still broken (circumstantial) — consistent with push_permission_granted/denied finding ¦ Build: Not started ¦ Status: setPersonProperties call not working(non logged in user)..working for logged in user
user_engagement | sign_in_prompt_shown | sign_in_prompt_shown | app | Anonymous user hits a sign-in wall ¦ event `sign_in_prompt_shown` fires | App — native screen (see trigger_steps) | any | super | method (google/apple/email) | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Anonymous user hits a sign-in wall | not working | 2026-08-29 | PostHog: Y (130 in 90d; first_seen 2026-08-01, none before) ¦ Customer.io: Y (4% of profiles) ¦ CONTRADICTS sheet — event fires with real volume since 2026-08-01; first_seen date suggests a fix landed around Aug 1; cannot confirm trigger correctness from volume alone ¦ Status: not working
user_engagement | sign_in_started | sign_in_started | app | Sign-in sheet method tapped ¦ event `sign_in_started` fires | App — native screen (see trigger_steps) | any | super | method (google/apple/email) | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Auth funnel top | Working | 2026-08-29 | PostHog: Y (1,513 in 90d) ¦ Customer.io: Y (51% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
user_engagement | sign_in_completed | sign_in_completed | app | Auth success → identify/alias merge ¦ event `sign_in_completed` fires | App — native screen (see trigger_steps) | any | super | method ¦ is_new_account | Yes |  | ios ¦ android | posthog ¦ customerio | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Registration rate; identity merge point | Working | 2026-08-29 | PostHog: Y (1,250 in 90d) ¦ Customer.io: Y (41% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
user_engagement | register | register | app | whenever someone registers for the first time ¦ event `register` fires | App — native screen (see trigger_steps) | logged-out | super | method | Yes |  | ios ¦ android | posthog ¦ firebase ¦ customerio ¦ singular | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Registration rate; identity merge point | Working | 2026-08-29 | PostHog: Y (250 in 90d) ¦ Customer.io: Y (19% of profiles) ¦ No known issue; confirmed live
user_engagement | signed_out | signed_out | app | Sign out ¦ event `signed_out` fires | App — native screen (see trigger_steps) | any | super | — | No |  | ios ¦ android | posthog ¦ customerio | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Account lifecycle | Working | 2026-08-29 | PostHog: Y (269 in 90d) ¦ Customer.io: Y (5% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
user_engagement | account_deleted | account_deleted | app | In-app deletion confirmed (Apple mandate) ¦ event `account_deleted` fires | App — native screen (see trigger_steps) | any | super | — | Yes |  | ios ¦ android | posthog ¦ customerio ¦ singular | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Compliance + CIO suppression | Working | 2026-08-29 | PostHog: Y (16 in 90d) ¦ Customer.io: Y (1% of profiles) ¦ No known issue; confirmed live, low volume as expected ¦ Build: Not started
ops | rating_prompt_shown | rating_prompt_shown | app | Streak Day-7 milestone / 3rd completion ¦ event `rating_prompt_shown` fires | App — native screen (see trigger_steps) | any | super | trigger | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Review-prompt reach (iOS hides outcome) | - | 2026-08-29 | PostHog: N (0 in 90d) ¦ Customer.io: N (not expected in CIO per sheet) ¦ Not firing in 90-day window ¦ Build: Not started ¦ Status: -
ops | error_shown | error_shown | app | User-facing error state ¦ event `error_shown` fires | App — native screen (see trigger_steps) | any | super | error_type (incl. offline) ¦ surface | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Ops — error surface map (crashes = Crashlytics) | ✓..working for error shown | 2026-08-29 | PostHog: Y (493 in 90d) ¦ Customer.io: Y (7% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started ¦ Status: ✓..working for error shown
ops | preferences_updated | preferences_updated | app | Post-onboarding prefs change ¦ event `preferences_updated` fires | App — native screen (see trigger_steps) | any | super | field (role/sectors/topics) ¦ new_value_count ¦ new_values | Yes |  | ios ¦ android | posthog ¦ customerio | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Preference drift; digest re-targeting | setPersonProperties call not working(non logged in user) | 2026-08-29 | PostHog: Y (209 in 90d) ¦ Customer.io: Y (3% of profiles) ¦ still broken (circumstantial) — consistent with the notification-family finding ¦ Build: Not started ¦ Status: setPersonProperties call not working(non logged in user)
ops | menu_item_tapped | menu_item_tapped | app | Profile → About item opened ¦ event `menu_item_tapped` fires | App — native screen (see trigger_steps) | any | super | item (terms/privacy/contact_us/faq/rate_app) | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Support-demand signal; rate_app complements rating_prompt_shown | Working | 2026-08-29 | PostHog: Y (469 in 90d) ¦ Customer.io: Y (4% of profiles) ¦ No known issue; confirmed live ¦ Build: Not started
ops | scroll_depth | scroll_depth | app | articles only. once per threshold per view (25/50/75/100) ¦ event `scroll_depth` fires | App — native screen (see trigger_steps) | any | super + story | depth_percent (25 / 50 / 75 / 100) | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | articles only. once per threshold per view (25/50/75/100) | Working | 2026-08-29 | PostHog: Y (2,512 in 90d) ¦ Customer.io: Y (20% of profiles) ¦ No known issue; confirmed live
ops | summary_expanded | summary_expanded | app | User expands the collapsible summary on an article or company card ¦ event `summary_expanded` fires | App — native screen (see trigger_steps) | any | super | surface (article_card / company_card) ¦ entity_or_story_id | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | User expands the collapsible summary on an article or company card | entity_or_story_id instead of story id | 2026-08-29 | PostHog: Y (1,048 in 90d) ¦ Customer.io: Y (17% of profiles) ¦ FIXED — renamed to story_id and correctly populated per surface ¦ Status: entity_or_story_id instead of story id
ops | profile_name_updated | profile_name_updated | app | User edits their name in Profile → Edit Profile and saves ¦ event `profile_name_updated` fires | App — profile tab | any | super | fields_changed (array: first_name / last_name) · new_first_name · new_last_name | No |  | ios ¦ android | posthog ¦ customerio | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | User edits their name in Profile → Edit Profile and saves |  | 2026-08-29 | PostHog: N (0 in 90d — event not found in PostHog taxonomy either) ¦ Customer.io: N ¦ STILL BROKEN — absent from BOTH PostHog and Customer.io despite sheet marking both as expected (escalates prior CIO-only finding)
content | article_published | article_published | app | Editorial team publishes an article (server-side; emitted to CIO to trigger sends) ¦ event `article_published` fires | App — in-article screen | any | story | story_id ¦ title ¦ url | No |  | ios ¦ android | posthog ¦ customerio | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | Editorial team publishes an article (server-side; emitted to CIO to trigger sends) |  | 2026-08-29 | PostHog: N (0 in 90d — not found in PostHog taxonomy) ¦ Customer.io: Y (<1% of profiles) ¦ Sheet marks PostHog checked but event not observed in PostHog in 90-day window
lifecycle | Application Backgrounded | Application Backgrounded | app | Perform the in-app action for `Application Backgrounded` ¦ event fires (observe in Live Events) | App — native | n/a |  | SDK-sourced — $lib=posthog-react-native, $lib_version=4.53.3 (30d sample, 5,585 events). SAME SDK instance as app_opened — this is PostHog's own React Native SDK's built-in application-lifecycle autoc | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | needs product owner + engineering decision — confirm whether PostHog SDK's captureApplicationLifecycleEvents autocapture should be disabled now that app_opened is manually instrumented, to avoid redundant tracking. Not a rogue SDK — same posthog-react-native instance, same codebase. | Possible duplicate/parallel tracking — needs product decision (app_opened and Application Opened are within 1.4% of each other in volume: 3,710 vs 3,763 in 90d) | 2026-08-29 | Volume: PostHog: 8,241 in 90d, confirmed live through 2026-08-29; CIO: 54% of profiles (engagement share)
lifecycle | Application Foregrounded | Application Foregrounded | app | Perform the in-app action for `Application Foregrounded` ¦ event fires (observe in Live Events) | App — native | n/a |  | n/a — event doesn't exist in PostHog, so $lib cannot be checked directly for it. Closest PostHog analog by volume/semantics is 'Application Became Active' (same posthog-react-native SDK, see that row) | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | needs product owner + engineering decision — confirm with whoever set up the Customer.io mobile SDK whether 'Application Foregrounded' is that SDK's own lifecycle autocapture (parallel to PostHog's) or maps 1:1 to 'Application Became Active' | NAMING MISMATCH / possible duplicate — needs product decision (unclear if this is CIO's own name for PostHog's 'Application Became Active', or an entirely separate CIO-side auto-tracked event) | 2026-08-29 | Volume: CIO: 85% of profiles (engagement share); PostHog: 0 — this exact event name does not exist in PostHog's taxonomy at all (confirmed on two separate queries)
lifecycle | Application Installed | Application Installed | app | Perform the in-app action for `Application Installed` ¦ event fires (observe in Live Events) | App — native | n/a |  | SDK-sourced — same posthog-react-native SDK family as the other Application_ events; taxonomy confirms PostHog SDK autocapture, not Firebase/Segment/a separate SDK | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | needs product owner + engineering decision — same SDK-autocapture dedupe question as the other Application_ events, PLUS confirm why PostHog volume dropped to near-zero after 2026-07-10 despite CIO showing ongoing volume | Possible duplicate/parallel tracking — needs product decision (duplicate of app_installed on the main sheet); ALSO appears to have stopped firing after 2026-07-10, a separate issue from the dedupe question | 2026-08-29 | Volume: PostHog: only 4 in 90d, last_seen 2026-07-10 — has stopped firing; CIO: 3% of profiles (much higher share than PostHog's near-zero volume)
lifecycle | Application Opened | Application Opened | app | Perform the in-app action for `Application Opened` ¦ event fires (observe in Live Events) | App — native | n/a |  | SDK-sourced — $lib=posthog-react-native, $lib_version=4.53.3 (30d sample, 2,579 events). SAME SDK instance as app_opened — PostHog SDK's built-in autocapture, not a third-party SDK. | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | needs product owner + engineering decision — same as Application Backgrounded: confirm whether to disable PostHog SDK's autocapture now that app_opened is manually instrumented | Possible duplicate/parallel tracking — needs product decision (app_opened and Application Opened are within 1.4% of each other in volume: 3,710 vs 3,763 in 90d — strong signal these fire on the same trigger) | 2026-08-29 | Volume: PostHog: 3,763 in 90d, confirmed live through 2026-08-29; CIO: 40% of profiles
lifecycle | brief_open_today | brief_open_today | app | Perform the in-app action for `brief_open_today` ¦ event fires (observe in Live Events) | App — Brief tab / brief cards | n/a |  | Not spot-checked | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | needs product owner decision — safe to remove/deprecate, confirmed dead in PostHog too | CONFIRMED Dead-test event — PostHog shows zero volume after 2026-07-13, over 6 weeks of silence | 2026-08-29 | Volume: PostHog: 112 in 90d, but last_seen 2026-07-13 — event has NOT fired since mid-July, confirms dead-test classification; CIO: <1% of profiles
lifecycle | brief_story_rated | brief_story_rated | app | Perform the in-app action for `brief_story_rated` ¦ event fires (observe in Live Events) | App — Brief tab / brief cards | n/a |  | channel property still NULL on all 5 samples checked 2026-08-29 (see App Audit tab, card_rated row) — the sheet's admitted card_rated channel bug carries over under the new name | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | update sheet to match reality (rename card_rated to brief_story_rated) AND fix production (channel still broken) | CONFIRMED RENAMED — card_rated does not fire in PostHog under that name at all; brief_story_rated fires instead with the same rating semantics. channel bug still present. | 2026-08-29 | Volume: PostHog: 89 in 90d, confirmed live through 2026-08-26; CIO: 2% of profiles
lifecycle | company_untracked | company_untracked | app | Perform the in-app action for `company_untracked` ¦ event fires (observe in Live Events) | App — company profile / companies | n/a |  | Not spot-checked | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | needs product owner decision — confirm whether this was replaced by watchlist_entity_removed or genuinely deprecated | Property mismatch (candidate) — appears to have stopped firing after 2026-07-28, over 4 weeks of silence | 2026-08-29 | Volume: PostHog: 27 in 90d, last_seen 2026-07-28 — has NOT fired since; CIO: <1% of profiles
lifecycle | industry_untracked | industry_untracked | app | Perform the in-app action for `industry_untracked` ¦ event fires (observe in Live Events) | App — native | n/a |  | Not spot-checked | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | needs product owner decision — likely deprecated alongside company_untracked | Property mismatch (candidate) — appears to have stopped firing after 2026-07-29, same dead pattern as company_untracked | 2026-08-29 | Volume: PostHog: 14 in 90d, last_seen 2026-07-29 — has NOT fired since; CIO: <1% of profiles
lifecycle | push_priming_dismissed | push_priming_dismissed | app | Perform the in-app action for `push_priming_dismissed` ¦ event fires (observe in Live Events) | App — push notification open | n/a |  | Not spot-checked | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | update sheet to match reality | Confirmed correct (fires, just undocumented) — CONFIRMED live in PostHog | 2026-08-29 | Volume: PostHog: 36 in 90d, confirmed live through 2026-08-04; CIO: 2% of profiles
lifecycle | share_initiated | share_initiated | app | Perform the in-app action for `share_initiated` ¦ event fires (observe in Live Events) | App — native | n/a |  | Not spot-checked | No |  | ios ¦ android | posthog | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | update sheet to match reality — but confirm this funnel-top event is still expected to fire, given near-zero recent volume | Confirmed correct (fires, just undocumented) but extremely low volume and appears to have stopped after 2026-07-30 | 2026-08-29 | Volume: PostHog: only 6 in 90d, last_seen 2026-07-30 — very low and has NOT fired since; CIO: <1% of profiles
lifecycle | Application Became Active | Application Became Active | app | Perform the in-app action for `Application Became Active` ¦ event fires (observe in Live Events) | App — native | n/a |  | SDK-sourced — $lib=posthog-react-native, $lib_version=4.53.3 (30d sample, 4,871 events). SAME SDK instance as app_opened and the other Application_ events — PostHog SDK's built-in application-lifecycl | No |  | ios ¦ android | posthog ¦ see_that_row) | observe | Observe in PostHog App Live Events / RudderStack — cannot drive from Chrome | needs product owner + engineering decision — same SDK-autocapture dedupe question as the other Application_ events; also confirm with the Customer.io SDK owner whether this maps to their 'Application Foregrounded' | Possible duplicate/parallel tracking — needs product decision (part of the same SDK-autocapture family as Application Opened/Backgrounded) | 2026-08-29 | Volume: PostHog: 7,528 in 90d, confirmed live through 2026-08-29 — highest volume of the three SDK auto-lifecycle events (fires on every foreground return, not just cold start); CIO has no event under this exact name — CIO's closest analog is 'Application Foregrounded' (85% of profiles), unconfirmed if same event
Note on E1: HOW it fires: user/system steps, pipe-separated (Ashish sample style)
Note on F1: WHERE it fires: URL or app screen/component

## _Ashish_sample
event_group | event_name | display_name | property | trigger_steps | trigger_url | login_state | event_property_groups | custom_event_properties | trigger_identify_call | expected_traits | source | destinations | automatable | test_notes | description | audit_status | audit_date | audit_notes
search_action | Search | Search | inc42 | Click the search icon in the header ¦ type 'fintech' ¦ press Enter | https://inc42.com | any | page | search_query:string:required ¦ search_source:string | No |  | web | posthog ¦ customerio ¦ ga4 | auto |  | User performs a site search
user_engagement | Newsletter Subscribed | Newsletter Subscribed | inc42 | Scroll to the newsletter box on any article ¦ enter test email ¦ click Subscribe | https://inc42.com/buzz/ | logged-out | page ¦ user | newsletter_id:string:required ¦ signup_source:string:enum[homepage¦article_footer¦popup] | Yes | email ¦ full_name | web ¦ backend | posthog ¦ customerio ¦ moengage | auto | Use test email test+audit@inc42.com only — creates a real Customer.io profile | User subscribes to a newsletter
user_engagement | Save Story | article_bookmarked | inc42 | Open any article ¦ click the Save/bookmark icon | https://inc42.com/buzz/ | logged-in | article ¦ page |  | No |  | web | posthog ¦ customerio | auto | Requires test account logged in; unsave afterwards to reset state | User saves an article to bookmarks
user_engagement | Page View | Page View | datalabs | Load the Datalabs home page | TODO-datalabs-url | logged-in | page ¦ user ¦ device | dl_page_type:string:enum[Home¦Company Search¦Company Profile] | No |  | web | posthog ¦ ga4 | auto | Datalabs has its OWN GTM container and PostHog project — verify against those | Datalabs page view
user_engagement | Pro Trial | pro_trial_started | inc42 | DO NOT COMPLETE — stop at the Razorpay payment screen | https://inc42.com/pro | logged-in | page ¦ user ¦ pro | trial_type:string ¦ trial_stage:string | Yes | email ¦ plan | backend | posthog ¦ customerio ¦ mixpanel | manual | Payment flow — verify destination-side only (last 7 days occurrences) | User's pro trial begins
user_engagement | Article Bookmarked | article_bookmarked | app | Observation only — cannot be driven from Chrome |  | n/a | article |  | No |  | ios ¦ android | posthog ¦ customerio | observe | Check the app's RudderStack source Live Events + PostHog for recent occurrences | User bookmarks an article in the app
Note on E1: HOW it fires: user/system steps, pipe-separated (Ashish sample style)
Note on F1: WHERE it fires: URL or app screen/component