## App V2 Roadmap
# | Change | Description | Problem / Data Evidence | Expected Impact | Priority | Confidence | Dependency / Sequencing
1 | Brief page redesign | Progress indicator ("4/8, tap for next"), "Continue where you left off" CTA with deep-link to exact card, editorial headline rewrite so it reads as a series not one article | Card-1 cliff: 55% don't advance past card 1. This is navigation, not disinterest — 29% go back to cover, 26% expand summary, only 10% actually leave the app. 21% move backward/sideways inside the app. | Recovers the 21% moving backward/sideways. Sessions reaching card 8 without completing already open more articles (2.3 vs 1.46/session) — fixing the return path alone could lift completion 33% to 51%. | P0 | High | None — can ship independently
2 | Story card copy/layout fix | Fix contradictory "Read more (takes 30 seconds)" copy; separate 30-sec summary CTA from a distinct "Read full story" CTA | Contradictory copy fights the app's anti-infinite-scroll positioning; card-1 confusion is partly a clarity problem, not just a navigation problem. | Supports #1 — same root cliff, cheap fix, no new data required to justify. | P1 | Medium | Ship alongside #1 — same surface
3 | Article + Explore page card revamp | Redesign article reader and Explore article/company cards | Company funnel: funding to financial_overview cliff is -30pt (37 to 26 sessions). Explore overall: 50% of sessions touch zero content — but the follow-up dig shows this is a fast scan (81s median), not a stuck user; exit and 24-48h return rate are close to normal. | Real, targetable impact on the company-page cliff. For the 50% zero-touch rate: revamp alone likely will not move it — there is no feed-impression event today to prove whether the feed is thin or the headlines just do not land. | P1 | Medium | Impact on zero-touch rate unmeasurable until #5 (feed-impression event) ships
4 | Dark mode | Full dark theme across the app | No behavioral data ties to this — it is a satisfaction/parity ask raised in the 20 Aug Satya sessions, not a funnel fix. | Cannot be quantified against any funnel metric. Treat as retention/goodwill, not a metric-mover. | P2 | Low (no data signal) | None
5 | Event / instrumentation fixes | Fix app_installed under-fire (~5% of users never fire it), fix summary_expanded wrongly carrying story_id instead of company_id on company_page, instrument decode (zero telemetry today), confirm error taxonomy via SQL not the sampled PostHog panel, add is_internal flag, add a feed-impression event (cards/headlines seen in Explore) | Doesn't fix user behavior — fixes whether the other 10 items' impact can be measured at all. decode is the AI explainer that IS the app's core positioning and has zero telemetry today. | Without this, #1, #3 and #8's real-world impact is a guess next time anyone checks. Should run in parallel with everything else, not scheduled after. | P0 | High | Blocks reliable measurement of #1, #3, #8 — do not sequence last
6 | DataLabs filters (Explore company search/filter reliability) | Investigate and fix Elasticsearch indexing/query behavior behind Explore's company search and filters | 16% of searchers hit 3+ consecutive zero-result searches in one sitting, worst case 28 of 46 searches zero-result. 86% retry rather than abandon — demand is there, the tool is failing them. | Direct funnel recovery on the company-discovery path, since search feeds into company opens. Strongest quantified evidence of any item on this list. | P0 | High | None — independent backend fix
7 | Walkthrough redesign — convey what Brief is | Redesign the 4-step guided tour (brief -> explore_articles -> explore_companies -> watchlist) so it actually explains what Brief is and that it's personalized | Ravi Kumar (outside reviewer) could not answer "what is Brief?" even after using the app. Separately, the tour is why Explore's 82% "reach" reads as usage — 48% of Explore events happen inside the first 10 minutes of the tour, not from organic choice. | Fixes two problems at once: sets real user expectations (may reduce card-1 confusion), and makes future Explore-vs-Brief usage numbers trustworthy instead of tour-inflated. | P1 | Medium | Should ship before trusting any future Explore vs Brief usage comparison
8 | PostHog feature flags + A/B testing infra | Wire in PostHog feature flags (fail-closed, proxied endpoint); run 2 Brief-card variants as a live A/B test; A/B test a few critical Explore pieces only, not the full section | Not a fix itself — infrastructure to let #1 and #3's redesigns be tested against the current version instead of shipped on belief. | Lets the team know definitively whether #1/#3 actually move completion and engagement, rather than assuming a redesign helped. | P0 | High | Needs #5's clean events to read A/B results correctly