## AMJ QOP
Bucket | Sub Bucket | Quarterly Goals | May
Media
Brand | Campaigns | 5k Subscriptions + Brand Campaign: AI Shift, The Checkout | 1k Subscriptions + Brand Campaign: AI Shift, The Checkout
|  | 5k Registration, Datalabs Free Brand Campaign | 1k+ Registrations
|  | 2k Downloads/Registrations on Reports (Ecom + Upcoming + Existing) | 1k+ Downloads/Registrations on Ecommerce Report
Inc42 Positioning - Update all brand touchpoints with updated positioning
|  | AI Content + Brand Amplifaction, 50k interactions/month | Amplify AI content on social, 25k interactions on social
Social |  | 600K+ Monthly Interactions ORM | 400k Monthly Interactions Amplify AI content on social, 25k interactions on social 2 New Marketing-Led Formats
Video |  | 5 Mn+ Video Views & 100k Interactions Per Month AI Operator: 3-4 Videos/Week, 500k+ Views & 10k+ Interactions Event-Led Video Pipeline: 4-5 Videos/Week, 1Mn+ Views & 20k+ Interactions 2 Original Short (1-2 min) Formats (Story-Led, News Roundup): 3-4 Videos/Week, 1Mn+ Views & 20k+ Interactions 1 Youtube (10-15 min) Format (2 Videos/Week + 5 Reels/Week): 2Mn+ Views & 40k+ Interactions | AI Operator: 3-4 Videos/Week, 500k+ Views & 10k+ Interactions Event-Led Video Pipeline: 3-4 Videos/Week, 1Mn+ Views & 20k+ Interaction 1 Original Short (1-2 min) Formats (Story-Led or News Roundup): 3-4 Videos/Week, 1Mn+ Views & 20k+ Interactions
Marketing | Acquisition & Growth | WEIU (NS2) Funnel Optimisation & CRO for Onsite Registration Growth Onboarding & CLM Systems | Establish Reporting for WEIU & complete funnel Lock & deploy onboarding & CLM for Inc42 & Datalabs Establish impact of campaigns & CLM on funnel + set goals for June
| Product | Datalabs SEO/AEO Expansion Global Search v2 Unified Inc42+DL Experience Report Pages Revamp Inc42 App | Datalabs SEO/AEO Expansion Report Pages Revamp Deploy Inc42 App v1 Global Search v2
| Data | 95% DCI, DFI, DAI for all Funded Companies 500 Trend Based & High Value Early Stage Startups Adding 1k New Investors [From the existing DB] Social Intelligence Data Semantic Data Data Warehouse + Unified User Data with Reverse-ETL | 95% DCI, DFI, DAI for all X Funded Companies 500 Trend Based & High Value Early Stage Startups Adding 1k New Investors [From the existing DB] Social Intelligence Data v1 Data Warehouse + Unified User Data with Reverse-ETL Phase 1
| Infra & Systems | Reporting Dashboards, Automated Reporting + Insights for Media, DL, EFL & IPs Streamline Asana SOP Updates Automate Newsletters AI-Led Systems for IP Marketing AI-Led + HIL Customer Support via Freshdesk/Hubspot Analytics & Instrumentation Audit Internal AI Tools & Systems: News AI 2.0, Markets AI 2.0, AI Data Requests, AI Research on Inc42 Data | Reporting Dashboards, Automated Reporting + Insights for Media, DL, EFL & IPs Streamline Asana Analytics & Instrumentation Audit Internal AI Tools & Systems: News AI 2.0, Markets AI 2.0, AI Data Requests, AI Research on Inc42 Data
BrandLabs Marketing | Brandlabs Campaigns Delivery | On Time Delivery, Campaign Metrics, Organic vs Inorganic Split, Budget Saved
| Client Pipeline Influenced | MQLs (New, Returning) Inbound Marketing System
| Brand | BL Rebranding + Website BL Newsletter NPS Tracking
IPs | AI Summit | 1000+ ticket sales. 60%+ selection rate. 600 attendees. | 1000+ ticket sales. 60%+ selection rate. 600 attendees.
| AmplifAI | 150+ applications. 5 startups selected. Demo day at AI Summit. | 150+ applications. 5 startups selected. Demo day at AI Summit.
| D2CX Runway | 100+ applications, 15 shortlisted for Pitches 2nd Edition | 100+ applications, 15 shortlisted for Pitches 2nd Edition
| D2CX Converge | Editions TBD
| D2C Summit | 150 ticket sales, 50% selection rate | Complete pre-reg campaign, launch Phase 1 marketing & achieve 75 ticket sales
| D2C Retreat | Launch D2C Retreat 2026
| AI Workplaces | Lock Concept & Prep for Launch

## May MOP
Area | Bucket | Sub Bucket | Goals | Accountability | Consulted | Deadline | Divisions Involved | Team Members Involved | Completion Status | Progress (%) | Bottlenecks/Comments | 11 May - 17 May | 18 May - 24 May | 25 May - 31 May
IPs | IPs
| AI Summit |  | 1000+ ticket sales · 60%+ selection rate · 600 attendees | Vishvani | Utkarsh | 2026-05-27 | Marketing, Editorial, Sales | Vishvani, Bhavika, Amit | Completed | 85.7% |  | 200 ticket sales | 250 ticket sales | 125 ticket sales
| AmplifAI |  | 150+ applications · 5 startups selected · Demo day at AI Summit | Saumya | Utkarsh | 2026-05-11 | Marketing, BL | Saumya, Bhavika | Completed | 100% |  | - | - | -
| D2C Summit |  | Complete pre-reg campaign · 150 ticket sales | Nityam | Utkarsh, Pooja | 2026-05-31 | Marketing, Editorial | Nityam, Animesh | In Progress | 40% | 58 tickets sold as of 31st may | Launch pre-reg campaign 50 Ticket Sales | 50 Ticket Sales Prep for Phase 1 Marketing | 50 Ticket Sales Phase 1 Marketing Ready To Launch
| D2CX Runway |  | 100+ applications · 15 shortlisted for Pitches · 2nd Edition kickoff | Nityam | Utkarsh, Pooja | 2026-05-31 | Marketing, BL | Nityam, Animesh | Completed | 100% | completed | - | - | TBD
| D2CX Converge |  | Launch Season 2 Marketing | Arminder | Utkarsh, Pooja | 2026-05-31 | Marketing, BL | Arminder | Delayed | 0% |  | - | Prep For Launch | Launch Season 2 Marketing
Media | Media
| Social | Inc42 Social Growth | 400K monthly interactions · 2 new marketing-led formats | Arminder | Utkarsh, Pooja | 2026-05-31 | Marketing, Design | Arminder, Tanya, Ananya | In Progress | 75% | 400K monthly interactions numbers achieved with 330.5K quality engagements, Finalised new carousel format, Marketing Format: Picking up various Industries from datalabs, working on report recurring task, New superhero templates for Check out newsletter | Social media reporting locked & automated 2 new carousal templates 1 new marketing-led format | 3 New Superhero Templates/Formats | 1 new marketing-led format
| Social | AI Content Amplification | Amplify AI content on social (25K interactions on social) | Arminder | Utkarsh, Pooja | 2026-05-31 | Marketing, Editorial | Arminder, Tanya, Ananya | Completed | 100% |  | Reporting Locked AI Summit Superheroes | AI Summit Superheroes Ongoing | AI Summit Superheroes Ongoing
| Newsletters | AI Shift, The Checkout, Daily Brief | 1K subscriptions · Brand Campaign | Nityam | Utkarsh | 2026-05-31 | Marketing, Editorial | Nityam, Animesh | In Progress | 20% | Plan made, execution yet to start | Reporting Locked Marketing Plan Locked | AI Shift + Checkout Marketing Campaign Launch | 1K+ Subscriptions
| Acquisition | Acquisition + WEIU (NS2) | Establish reporting for WEIU & complete funnel · Lock & deploy onboarding & CLM for Inc42 & Datalabs · Establish impact of campaigns & CLM on funnel + set goals for June | Nityam | Utkarsh, Tech | 2026-05-31 | Marketing, Tech | Nityam, Animesh, Prapti | In Progress | 70% | planning and reporting done, yet to deploy | Customer.io Hygiene/Setup + Properties + Tag/Segment Taxonomy Locked WEIU Reporting Locked Onsite Optins Optimisation Plan | Onsite Optins Optimisation Deployed L2 7-day onboarding sequence launched | L3 source-aware sequences launched
| Datalabs | Datalabs Free Launch — Activation | 1K+ registrations · Activation campaigns | Nityam | Utkarsh, Tech | 2026-05-31 | Marketing, Datalabs | Bhavika, Prapti | Delayed | 0% | yet to start | Context + Reporting + Master Messaging Doc | Marketing Plan + Common Messaging Doc + Assets | 1K+ Registrations
| Video | AI Operator | 3-4 videos/week · 500K+ views & 10K+ interactions | Tejas | Utkarsh, Pooja | 2026-05-31 | Video, Marketing | Tejas, Aditya, Video Team | Delayed | 0% |  | v2 Concept Note on Video Types & Scripts | 4 Videos Published | 4 Videos Published
| Video | Event-Led Pipeline | 3-4 videos/week · 1Mn+ views & 20K+ interactions | Aditya | Utkarsh, Pooja | 2026-05-31 | Video, Marketing | Tejas, Aditya, Video Team | In Progress | 10% |  | Video Reporting Locked & Automated | AI Summit Shoot Plan Locked (Series + Distribution-First Approach)
| Video | Original Short Format | 1 Original Short (1-2 min) format – Story-Led or News Roundup | Tejas, Aditya | Utkarsh, Pooja | 2026-05-31 | Video, Marketing | Tejas, Aditya, Video Team | Delayed | 0% |  | - | - | -
| Product | Datalabs SEO/AEO Expansion | Phase 1 SEO & AEO changes: Meta Tags Fixes, SSR -> CSR, Schema markups, Rel-Canonical changes | Alistin, Ashish | Utkarsh | 2026-05-31 | Tech, Marketing | Tech, Data | Completed | 100% |  | Phase 1 SEO & AEO changes: Meta Tags Fixes, SSR -> CSR, Schema markups, Rel-Canonical changes | Phase 1 + Phase 2 Review + Fixes | Phase 3 Plan + Kickoff
| Product | Report Pages Revamp + Global Search v2 | Report Pages Revamp (new template live) · Global Search v2 Launched | Alistin, Ashish | Utkarsh | 2026-05-31 | Tech, Marketing | Tech, Data | In Progress | 80% | Global Search is live, We are working on report page, which will be completed by 2nd June | - | Report Pages Revamp (new template live) · Global Search v2 Launched | -
| Product | Inc42 App v1 | Deploy Inc42 App v1 | Alistin, Ashish | Utkarsh | 2026-05-31 | Tech, Marketing | Tech | In Progress | 30% | Design is still ongoing, dev isn't started yet. | Lock concept note, PRD, scoping, feasibility & mapping | Alpha Version Scoping Locked + Build Starts | Alpha Version Ready, Testing, Prep for Launch
| Data | DCI / DFI / DAI Quality | 95% DCI/DFI/DAI for funded companies | Prapti | Utkarsh, Tech | 2026-05-31 | Tech, Data | Tech, Prapti, Data Team | Completed | 100% |  | TBD | TBD | TBD
| Data | Trend-Based Early-Stage Startups | 500 trend-based & high-value early-stage startups added | Prapti | Utkarsh, Tech | 2026-05-31 | Tech, Data | Tech, Prapti, Data Team | Completed | 100% |  | TBD | TBD | TBD
| Data | Investor Database Expansion | 1K new investors from existing DB | Prapti | Utkarsh, Tech | 2026-05-31 | Tech, Data | Tech, Prapti, Data Team | Delayed | 0% |  | TBD | TBD | TBD
| Data | Social Intelligence Data v1 | Social Intelligence Data v1 — pipeline ingestion live | Prapti | Utkarsh, Tech | 2026-05-31 | Tech, Data | Tech, Prapti, Data Team | In Progress | 60% | Have checked Linkedin Sales Nav from feasibility pov, now need to create pipelines | Scoping Locked | TBD | TBD
| Data | Data Warehouse | Data Warehouse + Unified User Data with Reverse-ETL — Phase 1 | Prapti | Utkarsh, Tech | 2026-05-31 | Tech, Data | Tech, Prapti, Data Team | In Progress | 70% | Need to pick reverse ETL | TBD | TBD | TBD
| Infra | Reporting Dashboards + Automated Reporting | Reporting Dashboards · Automated Reporting + Insights for Social, Video, Media, DL, EFL & IPs | Prapti | Utkarsh, Tech, Nityam | 2026-05-31 | Marketing, Tech, Data | Tech, Data | Yet To Start | 0% |  | Scoping Locked | TBD | TBD
| Infra | Internal AI Tools — AI Data Requests + AI Research | AI Data Requests pilot + AI Research on Inc42 Data pilot | Prapti | Utkarsh, Tech | 2026-05-31 | Tech, Data, Editorial | Tech, Data | Delayed | 0% |  | - | - | Scoping Locked
| Infra | Analytics & Instrumentation Audit | GA4 + PostHog + Customer.io audit & fixes | Alistin | Utkarsh, Tech | 2026-05-31 | Marketing, Tech | Marketing, Tech | In Progress | 40% |  | GA4 + PostHog + Customer.io audit & fixes | GA4 + PostHog + Customer.io audit & fixes | -
| Infra | Internal AI Tools — News AI 2.0 + Markets AI 2.0 | News AI 2.0, Markets AI 2.0 → production (in editorial newsroom) | Ashish | Utkarsh, Pooja | 2026-05-31 | Tech, Editorial | Tech, Data | On Track | 75% |  | Deploy to Editors + Feedback loop + Improvements | Deploy to Editorial Team | Feedback loop + Improvements

## June MOP
Area | Bucket | Sub Bucket | Goals | Accountability | Consulted | Deadline | Divisions Involved | Team Members Involved | Completion Status | Progress (%) | Bottlenecks/Comments
IPs | IPs
| D2C Summit |  | Complete pre-reg campaign · 300 ticket sales | Vishvani | Utkarsh, Pooja |  | Marketing, Editorial | Nityam, Bhavika | On Track | 77% | 232
| D2CX Runway |  | 100+ applications · 15 shortlisted for Pitches · 2nd Edition kickoff | Nityam | Utkarsh, Pooja |  | Marketing, BL | Nityam, Bhavika | Completed | 100%
| D2CX Converge |  | Launch Season 2 Marketing | Arminder | Utkarsh, Pooja |  | Marketing, BL | Arminder | Completed | 100%
| D2CX Retreat |  | Prep for Launch | [5 empty] | Delayed
| IP Infra |  | AI-Led Systems for IP Marketing | Nityam |  |  |  |  | Yet To Start | 0%
Media | Media
| Social | Inc42 Social Growth | 200K monthly interactions · 2 new marketing-led formats | Arminder | Utkarsh, Pooja |  | Marketing, Design | Arminder, Tanya, Ananya | Completed | 97% | 194K numbers achieved, Finaised 3 new carousel formats (design wise)
| Social | AI Content Amplification | AI content on social (25K interactions on social) | Arminder | Utkarsh, Pooja |  | Marketing, Editorial | Arminder, Tanya, Ananya | Completed
| Newsletters | AI Shift, The Checkout, Daily Brief | 2.5K subscriptions · Brand Campaign | Nityam | Utkarsh |  | Marketing, Editorial | Nityam, Animesh | Yet To Start | 0% | Depriotised
| Acquisition | Acquisition + WEIU (NS2) | Establish reporting for WEIU & complete funnel · Lock & deploy onboarding & CLM for Inc42 & Datalabs · Establish impact of campaigns & CLM on funnel + set goals for June | Nityam | Utkarsh, Tech |  | Marketing, Tech | Nityam, Animesh, Prapti | Delayed | 30% | Pending on Design front
| Datalabs | Datalabs Free Launch — Activation | 2.5K+ registrations · Activation campaigns | Nityam | Utkarsh, Tech |  | Marketing, Datalabs | Bhavika, Animesh, Prapti | In Progress | 20%
| Video | Event-Led Pipeline | 3-4 videos/week · 1Mn+ views & 20K+ interactions | Aditya | Utkarsh, Pooja |  | Video, Marketing | Tejas, Aditya, Video Team | In Progress | 50%
| Video | Original Short Format | 1 Original Short (1-2 min) format – Story-Led or News Roundup | Aditya | Utkarsh, Pooja |  | Video, Marketing | Tejas, Aditya, Video Team | Yet To Start | 50%
| Reports | Ecommerce Report | 1K+ downloads/registrations on Reports | Arminder | Utkarsh, Pooja |  | Research, Marketing | Sandeep, Arminder, Animesh | On Track | 74% | 735 downloads
| Product | Datalabs SEO/AEO Expansion | Audit & Improve SEO/AEO for Datalabs | Ashish, Prapti | Utkarsh |  | Tech, Marketing | Tech, Data | Completed | 100%
| Product | Report Pages Revamp + Global Search v2 | Report Pages Revamp (new template live) | Alistin, Ashish | Utkarsh |  | Tech, Marketing | Tech, Data | Completed | 100%
| Product | Inc42 App v1 | Deploy Inc42 App v1 | Alistin, Ashish | Utkarsh |  | Tech, Marketing | Tech | Delayed | 50%
| Data | DCI / DFI / DAI Quality | 95% DCI/DFI/DAI for funded companies | Prapti | Utkarsh, Tech |  | Tech, Data | Tech, Prapti, Data Team | On Track | 100% | Completed this month's target
| Data | Trend-Based Early-Stage Startups | 500 trend-based & high-value early-stage startups added | Prapti | Utkarsh, Tech |  | Tech, Data | Tech, Prapti, Data Team | Completed | 100%
| Data | Investor Database Expansion | 1K new investors from existing DB | Prapti | Utkarsh, Tech |  | Tech, Data | Tech, Prapti, Data Team | Delayed
| Data | Social Intelligence Data v1 | Social Intelligence Data v1 — pipeline live | Prapti | Utkarsh, Tech |  | Tech, Data | Tech, Prapti, Data Team | Completed | 100%
| Data | Social Intelligence Data | Internal AI Use cases 1. Editorial & Social Content Suggestions 2. Make Social Intelligence Data Queryable | Prapti | Utkarsh |  | Data, Tech | Data Team, Tech | On Track | 80%
| Data | Data Warehouse | Data Warehouse + Unified User Data with Reverse-ETL — Phase 2 | Prapti | Utkarsh, Tech |  | Tech, Data | Tech, Prapti, Data Team | On Track | 80%
| Infra | Reporting Dashboards + Automated Reporting | Reporting Dashboards · Automated Reporting + Insights for Social, Video, Media, DL, EFL & IPs | Prapti | Utkarsh, Tech, Nityam |  | Marketing, Tech, Data | Tech, Data | Yet To Start
| Infra | Internal AI Tools — AI Data Requests + AI Research | AI Data Requests pilot + AI Research on Inc42 Data pilot | Prapti | Utkarsh, Tech |  | Tech, Data, Editorial | Tech, Data | Yet To Start
| Infra | Analytics & Instrumentation Audit | GA4 + PostHog + Customer.io audit & fixes | Animesh | Utkarsh, Tech |  | Marketing, Tech | Marketing, Tech | In Progress | 20%
| Infra | Newsletters | Automate All Weekly Newsletters | Animesh | Utkarsh, Tech, Nityam |  | Tech, Editorial | Tech, Data | On Track | 80% | Markets Newsletter is Automated

## July MOP
Area | Bucket | Sub Bucket | Goals | Accountability | Consulted | Deadline | Divisions Involved | Team Members Involved | Completion Status | Progress (%) | Bottlenecks/Comments
IPs | IPs
| D2C Summit |  | 800 Ticket Sales (Cumulative) | Vishvani | Utkarsh, Pooja |  | Marketing, Editorial | Nityam, Bhavika | In Progress | 70%
| D2C Summit |  | Who Gets In Campaign | Nityam | Utkarsh |  | Marketing |  | In Progress | 50%
| D2CX Converge |  | 700 Applications | Arminder | Utkarsh, Pooja |  | Marketing, BL | Arminder | On Track | 100%
| D2C Retreat |  | 50 Applications | Vishvani | Utkarsh, Pooja |  | Marketing, Editorial | Nityam, Animesh | In Progress | 50%
| FAST42 |  | Marketing Launch | Nityam | Utkarsh, Pooja |  | Marketing, BL | Vishvani, Bhavika | Delayed
| IP Infra |  | AI-Led Systems for IP Marketing | Nityam | Utkarsh |  | Marketing | Nityam, Bhavika, Animesh | Delayed
Media | Media
| Brand | Brand v2 Rollout | Rollout Messaging v2 Across All Touchpoints | Nityam | Utkarsh |  | Marketing, Design | Nityam, Animesh | Delayed | 50%
| Social | Inc42 Social Growth | 220K monthly interactions · LI first formats | Arminder | Utkarsh, Pooja |  | Marketing, Design | Arminder, Tanya, Ananya | Completed | 100%
| Acquisition | Acquisition + WEIU (NS2) | Rollout Onsite Acquisition v2 Deploy CLM/onboarding for all touchpoints Establish reporting for WEIU & complete funnel | Nityam | Utkarsh, Tech |  | Marketing, Tech | Nityam, Animesh | Delayed | 50%
| Video | Event-Led Pipeline | 3 videos/week · 500k+ views & 10K+ interactions | Aditya | Utkarsh, Pooja |  | Video, Marketing | Tejas, Aditya, Video Team | In Progress | 57%
| Video | Original Short Format | 3 IPs - D2C, Deeptech, News + Trend Based | Aditya | Utkarsh, Pooja |  | Video, Marketing | Tejas, Aditya, Video Team | In Progress | 25%
| Reports | H1 Funding Report | 2K+ downloads/registrations on Reports | Arminder | Utkarsh, Pooja |  | Research, Marketing | Sandeep, Arminder, Animesh | In Progress | 25%
| Datalabs | Datalabs Campaign | Source Kya Hai Campaign Launch | Nityam | Utkarsh |  | Marketing, Datalabs | Bhavika | Delayed
| Datalabs | Datalabs Activation & Retention | Lifecycle Flows Bi-Weekly Digests Reactivation Campaign (1 Sequence + 2 EDMs) Watchlist + Alerts (TBD) | Bhavika | Utkarsh |  | Marketing, Datalabs | Data, Tech | In Progress | 30%
| Datalabs | Datalabs SEO/AEO Expansion | Audit & Improve SEO/AEO for Datalabs - SEO & AEO Phase 3 - Listicles Revamp & Crack Programmatic SEO/AEO via Listicles | Ashish, Prapti | Utkarsh |  | Tech, Marketing | Tech, Data | In Progress | 50%
| Datalabs | Ask Datalabs | Latency <10 sec Tracking & Feedback Loop | Alistin, Ashish | Utkarsh |  | Tech, Marketing | Tech, Data | In Progress | 50%
| App | Inc42 App v1 GTM | 5k+ Activated Users Ask Inc42 Social Intelligence Feed | Ranjith, Ashish | Utkarsh |  | Tech, Marketing, Data | Tech, Data | In Progress | 50%
| Data | DCI / DFI / DAI Quality | 95% DCI/DFI/DAI for funded companies | Prapti | Utkarsh, Tech |  | Tech, Data | Tech, Prapti, Data Team | Completed | 100%
| Data | Trend-Based Early-Stage Startups | 500 trend-based & high-value early-stage startups added | Prapti | Utkarsh, Tech |  | Tech, Data | Tech, Prapti, Data Team | In Progress | 50%
| Data | Investor Database Expansion | 1K new investors from existing DB | Prapti | Utkarsh, Tech |  | Tech, Data | Tech, Prapti, Data Team | Completed | 100%
| AI | Social Intelligence Data | Internal AI – Editorial & Social Content Suggestions | Prapti | Utkarsh |  | Data, Tech | Data Team, Tech | Completed | 100%
| AI | Internal AI Tools — AI Data Requests + AI Research | AI Data Requests pilot + AI Research on Inc42 Data pilot | Prapti | Utkarsh, Tech |  | Tech, Data, Editorial | Tech, Data | Delayed
| Infra | Data Warehouse | Data Warehouse + Unified User Data with Reverse-ETL — Phase 2 | Prapti | Utkarsh, Tech |  | Tech, Data | Tech, Prapti, Data Team | In Progress | 60%
| Infra | Analytics & Instrumentation Audit | GA4 + PostHog + Customer.io audit & fixes | Animesh | Utkarsh, Tech |  | Data, Marketing, Tech | Data, Marketing, Tech | In Progress | 30%
| Infra | Newsletters | Automate All Weekly Newsletters | Animesh | Utkarsh, Tech, Nityam |  | Tech, Editorial | Tech, Data | On Track | 50%

## July Sprint
Inc42 Sprint July 2026
Bucket | Sub-Bucket | Goal | People Involved | Founders Involved | Owner | Progress Status | Subjective Summary | Links | Bottleneck | Completion %
Videos | Video Series | Deeptech [Insta First] | Aditya Video Team Editorial | Utkarsh Pooja | Aditya | 50% Or Less
Videos | Video Series | D2C [Insta First] | Nityam Vishwani Aditya + Video Team | Utkarsh Pooja | Aditya | 50% Or Less
Videos | Video Series | Trends [YouTube First] | Bismah Aditya + Video Team | Utkarsh Pooja | Aditya | 25% Or Less
IPs | DRS 2026 | Close 30 Speakers Overall | Palak Agarwal Anshika | Pooja | Palak | 25% Or Less
IPs | DRS 2026 | Paid Confirmed Attendees - 200 | Nityam Vishwani Bhavika Sakshi | Utkarsh | Vishwani | 75% Or Less
IPs | DRS 2026 | 50 Free Attendees | Sakshi | Pooja | Sakshi | Yet to start
IPs | DRS 2026 | DRS Who Get's In Campaign Launch + Influencer Amplification | Vishwani Nityam | Utkarsh | Nityam | 25% Or Less
IPs | D2C Retreat | Website & Marketing Launch | Marketing | Utkarsh |  | Completed
IPs | D2C Retreat | Confirm 10 Attendees | Yash Nitika | Pooja Vaibhav | Yash | 50% Or Less
Editorial | Series Launch | Business Model Breakdown Series Launch | Meha Palak Sharma | Pooja | Meha | Completed
Editorial | Exclusives | 10 Exclusives | Editorial | Pooja | Vinay | Completed
Editorial | Report Design | Automate Report Design With Claude | Sandeep | Pooja Utkarsh | Sandeep | Completed
Courses | RetailX | Lock Curriculum & Concept Note | Shantanu | Utkarsh Pooja | Shantanu | Almost 100%
Courses | RetailX | Lock 3 Speakers + 10 Brand Names | Shantanu Palak Agarwal Anshika | Pooja | Palak | 25% Or Less
Courses | RetailX | Brand Identity + Website Brief Lock | Shantanu | Utkarsh | Shantanu | 25% Or Less
AI | Internal AI Tools | News AI & Markets AI Final Adoption | Editorial | Utkarsh Pooja | Nikhil | Completed
AI | Internal AI Tools | Social & Editorial Ideas Pipeline Agent Launch & Adoption | Nikhil Shishir Vinay Akshit Meha Prapti Tanuj Sandeep | Utkarsh Pooja | Prapti | Completed
AI | Internal AI Tools | Editorial Stories Feedback Agent Launch & Adoption | Nikhil Shishir Vinay Akshit Meha Prapti Tanuj Sandeep | Utkarsh Pooja | Prapti | Completed
Brand | Brand Refresh | Inc42 Brand v2 Rollout Across All Touchpoints | Nityam Animesh | Utkarsh | Nityam | 75% Or Less
Product & Marketing | App | Inc42 App (Ready To Go Live) | Product & Tech | Utkarsh | Ranjith | 75% Or Less
BrandLabs | Reports | Accounts Delivery Tracker | BrandLabs | Vaibhav | Sanjo | Almost 100%
BrandLabs | Internal Automated System | Asset Marketing Reports | BrandLabs | Vaibhav | Sanjo | 50% Or Less
BrandLabs | Dashboards | Consumption Dashboards | BrandLabs | Vaibhav | Sanjo | 25% Or Less
HR | Hiring | D2CX Sales | HR Shantanu | Utkarsh | Shweta | Completed
HR | Hiring | Sr. Visual Designer | HR | Utkarsh | Shweta | 75% Or Less

## Aug MOP
Area | Bucket | Sub Bucket | Goals | Accountability | Consulted | Deadline | Divisions Involved | Team Members Involved | Completion Status | Progress (%) | Comments/Bottlenecks
IPs | IPs
| D2C Summit |  | 900 Ticket Sales (Cumulative) | Vishvani | Utkarsh, Pooja | 2026-08-18 | Marketing, Editorial | Nityam, Bhavika | In Progress
| D2C Summit |  | Who Gets In Campaign | Nityam | Utkarsh | 2026-08-15 | Marketing, Social | Vishvani | On Track
| D2CX Converge |  | 700 Applications | Arminder | Utkarsh, Pooja | 2026-08-31 | Marketing, BL, Social | Animesh | On Track
| D2C Retreat |  | 30 Qualified Applications | Vishvani | Utkarsh, Pooja | 2026-08-31 | Marketing, Editorial | Nityam, Animesh | In Progress
| CTO Summit |  | Marketing Launch & 75 Ticket Sales | Vishvani | Utkarsh, Pooja | 2026-08-31 | Marketing, Editorial | Nityam, Bhavika | In Progress
Media | Media
| Brand | Brand v2 Rollout | Rollout Messaging v2 Across All Touchpoints | Nityam | Utkarsh | 2026-08-31 | Marketing, Design | Nityam, Animesh | Yet To Start
| Social | Inc42 Social Growth | 242K Monthly Interactions · 4 Recurring Series · ORM Tool + 90% Response Rates | Arminder | Utkarsh, Pooja | 2026-08-31 | Marketing, Design | Arminder, Tanya, Shivanshi | In Progress
| Acquisition | Acquisition + WEIU (NS2) | Rollout Onsite Acquisition v2 Establish reporting for WEIU & complete funnel | Nityam, Prapti | Utkarsh, Tech | 2026-08-31 | Marketing, Tech | Nityam, Animesh | Yet To Start
| Video | Event-Led Pipeline | 3 videos/week · 500k+ views & 5K+ interactions | Aditya | Utkarsh, Pooja | 2026-08-31 | Video, Marketing | Video Team | In Progress
| Video | Original Short Format | 2 videos/week D2C Series 1 video/week YT Series (10 min+) 200k+ views & 2K+ interactions | Aditya | Utkarsh, Pooja | 2026-08-31 | Video, Marketing | Video Team | In Progress
| Reports | Report | 1K+ downloads/registrations on Reports | Arminder | Utkarsh, Pooja | 2026-08-31 | Research, Marketing | Sandeep, Arminder, Animesh | Yet To Start
| Datalabs | Datalabs Activation & Retention | Lifecycle Flows Bi-Weekly Digests Reactivation Campaign (1 Sequence + 2 EDMs) | Bhavika | Utkarsh | 2026-08-31 | Marketing, Datalabs | Data, Tech | In Progress
| Datalabs | Datalabs SEO/AEO Expansion | Audit & Improve SEO/AEO for Datalabs - SEO & AEO Phase 3 - Listicles Revamp & Crack Programmatic SEO/AEO via Listicles | Prapti | Utkarsh, Ashish | 2026-08-25 | Tech, Marketing | Tech, Data | In Progress
| Datalabs | Payment & Dunning Systems | Dunning, Payment Retry, Payment URLs for Recovery & Abandons | Ashish | Utkarsh | 2026-08-21 | Tech |  | In Progress
| Datalabs | Ask Datalabs | Latency <10 sec Streaming, Fast Mode Tracking, Analytics & Feedback Loop | Ranjith, Ashish | Utkarsh | 2026-08-21 | Tech, Marketing | Tech, Data | In Progress
| App | Inc42 App v1 GTM | 1k+ Activated Users Ask Inc42 Social Intelligence Brief 50+ User Interviews & Feedbacks | Ranjith | Utkarsh | 2026-08-31 | Tech, Marketing, Data | Tech, Marketing, Data | In Progress
| Data | Trend-Based Early-Stage Startups | 500 trend-based & high-value early-stage startups added | Prapti | Utkarsh, Tech | 2026-08-31 | Data | Data | In Progress
| Data | Investor Database Expansion | 1K new investors from existing DB | Prapti | Utkarsh, Tech | 2026-08-31 | Data | Data | In Progress
| AI | Social Intelligence Data | Make Social Intelligence Data Queryable via Slack Company-Wide | Prapti | Utkarsh | 2026-08-21 | Data | Tech, Data | In Progress
| AI | Internal AI Tools — AI Data Requests + AI Research | AI Data Requests pilot + AI Research on Inc42 Data pilot | Prapti | Utkarsh, Tech | 2026-08-31 | Tech, Data, Editorial | Tech, Data | Yet To Start
| Infra | Data Warehouse | Data Warehouse + Unified User Data + Event Analytics with Reverse-ETL Deployed | Prapti | Utkarsh, Tech | 2026-08-31 | Tech, Data | Tech, Prapti, Data Team | In Progress
| Infra | Server & Cost Optimisation | Migrate & consolidate all servers/systems to Azure and optimise cost by 30% | Ashish | Utkarsh | 2026-08-31 | Tech | Tech | In Progress
| Infra | Analytics & Instrumentation Fixes | GA4 + PostHog + Customer.io audit & fixes | Bhavika, Animesh | Utkarsh, Tech, Data | 2026-08-31 | Data, Marketing, Tech | Data, Marketing, Tech | In Progress
| Infra | Newsletters | Automate All Weekly Newsletters | Animesh | Utkarsh, Tech, Nityam | 2026-08-31 | Tech, Editorial | Tech, Data | In Progress

## FY27 Plan — Engines × Tracks
FY27 Plan — Engines × Tracks
One horizon plan · LOCKED 2026-08-21 (Utkarsh): O2 Audience runs on the strategy's engine verbs — Acquire & Identify → Activate & Deepen → Retain & Renew — journey stages of one person across all surfaces; per-product work lives in the MOP, serving a stage. Lanes match the Sept MOP.
Track | What it means in plain terms | Owner | Waits on | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
NEWSROOM – upstream of all three engines
Newsroom | Journalism powers all three engines and answers to none – the trust everything borrows | Editorial | – independent | ● Operating model adopted – editorial placed upstream, interfaces named | ◐ Editorial Feedback Loop restarted | ● METRIC DECIDED – return-attribution vs parked R30 (habit line) + citations (authority line) vs others |  | ◇ | ◇ | ◇ | ◇
O1 · BRAND & DISTRIBUTION
Brand & Campaigns | One Inc42 message, told the same way everywhere | Nityam | – | ● Brand v2 rollout starts – agreement done, work can begin | ● Message live across Inc42 media ● Extend to Datalabs and the App, not just media ● Perception survey sent ● Inc42 Design System v1 ● IP Design System | ● One message across all three services ● Read the perception baseline ● Inc42 master brand campaign work kickoff ● Design refresh & unification work kickoff ● Founder branding kickoff with positioning & calendar ● Employer branding kickoff | ● Inc42 master brand campaign work ● Design refresh & unification work ● Founder branding ● Employer branding | ● Year in Review ships ● Inc42 master brand campaign work ● Design refresh & unification work ● Founder branding ● Employer branding | ● Outlook 2027 ships | ◇ | ◇
Social | The engine's daily reach – handles, platforms, series. Voice: raw, authentic, personality, aspiration | Arminder | – | ● 242K monthly interactions ● 4 Series ● ORM Tool Locked | ● Series shipping on the owner grid ● Expand focus to Twitter and Facebook ● ORM at 90% reply rate | ● Cadence holds ● ORM at 100% reply rate | ● Cadence holds | ◇ | ◇ | ◇ | ◇
Video | Explainers, news roundups/show, series & flagship – the seam between newsroom and brand | Aditya | – | ● D2C Reels IP at 2x/week ● Youtube Explainer Series at 1x/week | ● 500k+ views/m, 5k+ Interactions ● D2C Reels IP at 2x/week ● 2 New Reels IP Piloted ● Youtube Cadence Solidified | ● Existing cadence continues (3 Reel IPs, 1 YT IP) ● 1 New YT IP Kickoff ● Flagship video IP/podcast work kickoff | ● 1Mn+ views/m, 10k+ Interactions ● Existing Cadence continues ● Flagship video IP launch | ◇ | ◇ | ◇ | ◇
Distribution | The multiplier on everything above – influencer, amplification, UGC, citations | Nityam | Citations instrumentation | ▢ Scope | ● Citations tracking starts – feeds the perception KPI | ◇ Influencer & amplification playbook from what Brand v2 shows | ◇ | ◇ | ◇ | ◇ | ◇
O2 · AUDIENCE
Measurement & Data Activation | See the audience properly, fix what we cannot see – and USE what we already know without waiting for the rest | Prapti (warehouse & data activation) · Ranjith (instruments) | Data Activation waits on NOTHING – that is the point. Measurement waits on the 30-day clock (product) | ● Record when our tracking broke, so trends stop lying ● Clean up duplicate and dead data ● Pipe app activity into the warehouse – recovers 3 activity types at once 🔴 ● Onboarding (seniority + company) at APP SIGN-IN (not signup – 3 in 4 app users already have an account) ● Fix and set audit process for all analytics (events, properties) across Inc42, Datalabs, App, IPs ● Fix reading-depth (scroll) tracking ● Fix duplicate-person merging in the app ● Do-not-contact and safety rules in place ● Agree which fields we push and who depends on them ● First Reverse ETL push live | ● One profile per person across web, data, email and app ● Turn on the Datalabs 30-day counter – recovers a whole activity type ● Day-by-day view of what each person did ● NORTH STAR MEASURABLE PROPERLY for the first time ● Tracking changeover completes (~20 Sep) ◇ Product picks what to build from what engagement data shows ● Restart contact with 93,000 dormant reachable people ● Push the engagement tier into the messaging tool ● Segments built on engagement score go live | ● See who uses more than one product ● Build the engagement score on real data ● Set the engagement tiers from evidence, not opinion ◇ Product picks what to build from what engagement data shows ● Full behavioural targeting | ◇ | ◇ | ◇ | ◇ | ◇
Unification | Making Inc42 feel like one product instead of five separate ones | Utkarsh (chair) → Ranjith at delivery Nityam owns the brand/messaging half | Identity spine (Sep, Engine tab) | ● Agree what "One Inc42" actually means – the seam decision nobody owns today ● Write it down: one login, one navigation, one value proposition – a dated document, not a discussion ● Audit where the three services contradict each other today ● Lifecycle journeys ship for Datalabs and the App SEPARATELY (unification comes after, by design) | ● UNIFICATION PLAN shipped – one design for messaging, navigation, onboarding and lifecycle journeys across Inc42, Datalabs, App (plan in Sept, delivery phased) ● Cross-surface use measurable for the first time (1.6–3.4% today) | ● Hands over to Ranjith for delivery ◇ Which cross-surface paths to build next, from what people actually use | ◇ | ◇ | ◇ | ◇ | ◇
Acquire & Identify | Do the right people ARRIVE — and do we learn who they are at the door? One person, any surface | Growth + Ranjith (gates & capture) · Nityam (acquisition) | App sign-in capture (Aug) | ● App is live (12 Aug) ● Marketing ramp begins w/c 25 Aug ▶ ● Seniority + company asked at app sign-in ⚠ Web acquisition goal still targets WEIU – needs rewriting | ● App marketing at full scale ◐ Sign-up gate test on web (onsite freewall & newsletter locks) ● ONE onboarding pattern agreed across all three services | ◇ Product picks what to change from what the gate test shows | ◇ | ◇ | ◇ | ◇ | ● Signup→identified conversion read (the stage's number)
Activate & Deepen | Does a known person form a HABIT in the first weeks — and reach a second surface? The mechanism competition runs INSIDE this stage: candidates compete on 30-day return, winners get investment, losers get dropped | Ranjith (runs) · Utkarsh (scores) | Engagement scoring (Oct, Measurement track) | ● App notifications for Brief & Breaking cadence ● Datalabs Newsletter · Social Briefing (Pulse) – candidates named ▶ ● Lifecycle journeys ship for Datalabs and the App SEPARATELY | ● Alerts, community and report surfaces scoped ● Unification plan folds the journeys into one design (with the Unification track) | ● FIRST SCORING – every candidate measured on 30-day return, on real data ● Journeys running on real engagement segments | ● Winners get investment, losers dropped – visibly, so the discipline is real | ● Winners become the membership's candidate entitlements | ◇ Second round | ◇ | ● Persistence read – did the 34%→94.5% frequency yardstick move?
Retain & Renew | MONTHS later, are they still here — and did we ask them to stay? Reactivation, win-backs, renewal, payment recovery | Ranjith (renewal + in-product) · Animesh (campaigns) | First warehouse push (Aug) + segments (Sep) | ▶ ● Payment retries and dunning – recovers failed payments | ▶ ● Reactivation sequence to the 93K dormant reachable pool ● Datalabs renewal motion, Plus new & existing memberships call | ● Win-backs running on engagement segments | ◇ | ◇ | ◇ | ◇ | ● Renewal rate read vs today's 15%
AI Layer (Ask) | Ask Inc42 – answers drawn from our own data, on every surface | Ranjith + Ashish | – nothing. Already shipping | ▶ ● Ask Datalabs: streaming and fast mode ship (21 Aug) ▶ ● Ask Inc42 live in the app | ● Decide whether Ask goes on Inc42.com, and build it ● Start counting Ask queries – one of only two audience activities we cannot currently see at all | ● Ask live on all three surfaces ● Usage and answer quality measured | ◇ Does the AI layer sit inside the paid membership or stay free – decided on usage, not opinion | ◇ | ◇ | ◇ | ◇
Offering | Learning what people would actually pay for, before we build it | Ranjith + Utkarsh | Engagement evidence (Oct) + A1 probe |  | ● Price probe on existing subscribers ◇ Read the probe | ◐ Engagement evidence builds up | ◇ Shape the offering from what people actually use | ◇ Define the membership candidate | ◇ Design the pilot | ◇ | ◇ Pilot runs early FY28
O3 · IPs, EVENTS & COMMUNITIES
Flagships & Editions | Which rooms land when – milestones only; the IP calendar tab stays the source of truth | Per-IP owners | IP calendar | ● D2C Summit delivered (19 Aug) | ● CTO Summit (30 Sept) · D2C Retreat (17–19 Sept) | ● FAST42 marketing starts | ● AI Workplaces launch | ◇ | ◇ | ● FAST42 event · Tech Rich List | ◇
Cohorts & Communities | Do the recurring formats compound – cohorts, dialogues, the club cadence | Per-IP owners | – | ● D2CX C10 starts (Aug end) | ● D2CX C10 starts (Aug end) ● Convocation 22–23 Sept | ● Basecamp 3–5 Oct ● RetailX C1 Starts | ◐ C11 starts (Nov end) | ◇ Dialogues cadence read | ◇ | ◐ C12 starts (Feb mid) | ◇
IP Capability | Does the portfolio get the machinery – QAA, per-edition P&L, the per-IP-GM model | Per-IP owners · Utkarsh (QAA rule) | Events-team sheets (the QAA instrument) | ● QAA adopted – same qualification bar as QIA, never a second definition ● Events-sheets ask scoped: which events, which columns, who sends · CTO Summit + D2CX Convocation + Retreats delivered (Sept MOP) | ● AI Led IP Marketing System (Brand, Comms, Outreach, Analysis, etc) | ◇ | ◇ | ◇ | ◇ | ● FAST42 event (Feb) | ◇ QAA in every edition report
O4 · ENGINE ROOM
Internal AI & Agent Platform | The AI that runs the company – pilots, adoption, the agent platform. A11: cost per QIA roughly flat while QIA scales | Prapti (pilots) · Ranjith (platform, per S5) | QIA measurable (~Oct) for the cost line | ▶ ● Social intelligence queryable via Slack | ● AI Data Requests + AI Research pilots live | ● Adoption push toward the 20–30-user mandate · cost-per-QIA baseline (first measurable month) | ◐ Cost line reported monthly | ◇ | ◇ | ◇ | ● A11 read: cost flat while QIA multiplied?
Automation & Infra | The boring compounding – automation, templates, the design system, the servers | Animesh · Ashish · Akshay (design system) | – | ▶ ● Newsletter automation · Azure migration in flight | ● Invoicing & Support automation · ≥2 repeat formats templated ● Server migrations close-out + cost stabalisation | ◇ Next automation targets from ops pain | ◇ | ◇ | ◇ | ◇ | ● Cost base read vs Aug
NOTES — carried forward from the pre-lock plan
1. CROSSWALK to the MOP: lanes match 1:1. In O2, MOP rows are SURFACES (App, Datalabs, Data…) serving journey-stage tracks — read the Serves column; one surface may serve different stages in different months. Every MOP Serves value must name a track here; the Monday serves-check enforces both directions.
2. ▶ marks work already running as a MOP goal — this tab gives it a destination, it is not new work landing on top.
3. 🔴 We currently compute the north-star on 3 of its 9 defined activities; most of the rest are already tracked and just not piped into the warehouse. WHEN THOSE SWITCH ON THE NUMBER WILL JUMP — that is a measurement fix, NOT growth, and must not be banked as growth.
4. The app launched 12 Aug. Three in four app users are existing accounts signing IN — so capture happens at sign-in, not signup. The 30-day tracking changeover is calendar time: started in Aug it clears ~20 Sep; later, everything after moves with it.
5. Unification is chaired (Utkarsh) because it cuts across product, brand, Datalabs and the app — it graduates to Ranjith once "One Inc42" is defined in writing. The mechanism competition inside Activate & Deepen is a competition, not a delivery plan: evidence decides which survive.
6. ⚠ marks known-stale items left visible on purpose (e.g. the web acquisition goal still citing a retired metric) — fixed at the MOP review, not silently here.
7. Lanes have opposite shapes on purpose: Audience lands by ~Oct then runs; Brand / IP / Engine Room fill as evidence arrives. Newsroom and IP lanes are thin BY DESIGN — first horizon entries, not incomplete plans.
8. Griffin is out of scope on this plan and the MOP (Utkarsh, 2026-08-21) — it runs on the Griffin desk with its own cadence.
WHAT WE DELIBERATELY HAVE NOT DECIDED YET (merged register – single source)
Decision | Who decides | When | What tells us the answer
What "One Inc42" actually means in the product | Utkarsh | Sep | A written definition – that document IS the deliverable, not a meeting
Who owns unification after October | Utkarsh | Oct retro | Whether "One Inc42" is defined in writing and the August instrument work has landed — then delivery moves to product
Which retention mechanisms survive → get investment | Utkarsh scores (Oct) · Ranjith invests (Nov) | Oct → Nov | 30-day return lift – measured, not argued
What the membership contains | Ranjith + Utkarsh | Dec | What engaged people actually use, not what we assume
Price and packaging | Utkarsh | Sep | The price probe on existing subscribers
Whether the sign-up gate stays | Ranjith | Oct | The gate test – does it cost more traffic than it gains identity
Does the AI layer sit in the paid tier or stay free | Ranjith + Utkarsh | Nov | Real Ask usage across the three surfaces
Editorial's metric (habit line) | Utkarsh + Editorial | ~Oct | Return-attribution credibility from the scoring work; R30 parked unless it fails
How the three services' messages converge | Nityam | Sep | Brand v2 rollout plus the perception baseline
Consent rules for marketing | Prapti → legal | Oct | Best-practice research, then legal sign-off
Whether to merge our 3 messaging workspaces | Utkarsh | TBD | Separate discussion – not blocking anything

## Sept MOP
SEPT MOP — RATIFIED & LOCKED 2026-08-21 (Utkarsh). Lanes = the FY27 Plan lanes; every row's Serves resolves to a track there (serves-check runs Mondays 09:40). Griffin out of scope here — tracked on the Griffin desk.
Lane | Bucket | Goals | Accountability | Consulted | Deadline | Serves | Notes / provenance
NEWSROOM (upstream of all three engines)
NR | Editorial | (existing editorial cadence rows carry as-is) | Editorial | Utkarsh | 30 Sept | Newsroom → Audience interface (the return reason) | Editorial metric decision lands ~Oct with the scoring work — no metric row until then
O1 · BRAND & DISTRIBUTION
O1 | Brand | 2 brand campaigns shipped · recall measured against the JAS baseline · Brand v2 message live across Inc42 media + extended to Datalabs & App | Nityam | Utkarsh | 30 Sept | Brand & Distribution · Brand & Campaigns | OND focus IS brand (no new IP launches). Extension to all three services per the Product & Brand tab
O1 | Social | Monthly interactions target (rebaseline post-Aug) · series shipping on the owner grid | Arminder | Utkarsh, Pooja | 30 Sept | Brand & Distribution · Social | Carry: series owners+dates were overdue in Aug
O1 | Video | Per the video plan — ⚠ REBUILD FIRST: draft is built around departed Tejas; Aditya interim. Owner set 08-21: Aditya | Aditya | Utkarsh | 30 Sept | Brand & Distribution · Video
O1 | Campaigns | Perception survey SENT — overdue since July (the brand vision's own Q2 gate) | Nityam | Utkarsh | 15 Sept | Brand & Distribution · Brand & Campaigns | NEW from the Product & Brand tab — the T0 for every brand read
O2 · AUDIENCE
O2 | Measurement | Identity spine live (web+Datalabs+email+app leg) · Datalabs 30-day counter ON · app events piped · NORTH STAR PROPERLY MEASURABLE | Prapti (data/warehouse) · Ranjith (implementation) | Utkarsh | per roadmap v2 Wave 1–2 | Audience · Measurement & Data Activation | REWRITTEN from the 08-12 draft: baseline is DONE (pulled+verified 08-14/15); owner updated per the warehouse ownership decision (was Nityam+Prapti). Dates from 62-warehouse-roadmap-v2.md
O2 | Unification | "One Inc42" WRITTEN DEFINITION shipped — one login, one navigation, one value proposition; the document IS the deliverable | Utkarsh (chair) | Ranjith, Nityam | 30 Sept | Audience · Unification | NEW — the Sept gate for unification's graduation to Ranjith (Oct retro). Was in the AOP plan, missing here
O2 | Activation | First reverse-ETL push LIVE — 26K qualified reachable by role · reactivation sequence to the 93K dormant pool · engagement tier pushed to Customer.io | Prapti + Growth | Utkarsh | 30 Sept | Audience · Measurement & Data Activation | NEW from the Audience Engine tab — was in nobody's September
O2 | Retention | 🔴 RENEWAL MOTION BUILT — 15% auto-renew today; 26–142 Plus terms end monthly with zero communication | Ranjith | Utkarsh | 30 Sept | Audience · Retain & Renew | OWNED 08-21: renewal comms → product (Ranjith), consistent with membership-line ownership. Was the largest unclaimed lever (see tiers workbook §5)
O2 | Acquisition | Onsite acquisition v2 live · qualified signups from bought channels baselined · gate test STARTED (Register Lock restored first) | Nityam (Animesh runs) | Utkarsh | 30 Sept | Audience · Acquire & Identify | The interim lane's first month with a number. Gate test per A2 — holdout needs Register Lock back
O2 | Acquisition | Reports distribution target | Arminder | Utkarsh | 30 Sept | Audience · Acquire & Identify | Moved into O2/Acquisition by Utkarsh 08-21 — reports drive downloads→registrations. Editorial still supplies the report itself (Newsroom interface)
O2 | Datalabs | Lifecycle: campaign sequences live (marketing) · behavioural alerts scoped (product) · Datalabs onboarding DESIGNED (the only service without one) | Animesh · Ranjith | Utkarsh | 30 Sept | Audience · Activate & Deepen | First month under the lifecycle split + onboarding gap from the Product & Brand tab
O2 | Datalabs | Payment leak Sprint 2 close-out + B1 mobile + B2 filters (deferred from Aug) | Ranjith (owner) · Ashish (build) | Utkarsh, Prapti | 30 Sept | Audience · Retain & Renew | Payments → product per the ownership map. Involuntary churn — distinct from the renewal row
O2 | App | Activation target vs the Aug baseline · employer+seniority capture at SIGN-IN live · 30-day tracking clock CLEARS (~20 Sept if started Aug) | Ranjith | Utkarsh | 30 Sept | Audience · Acquire & Identify · coverage | UPDATED: app launched 12 Aug; sign-in outnumbers register 3:1 so capture moves to sign-in; identify() already solved (98.3%)
O2 | AI (Ask) | Ask on Inc42.com DECIDED and building (third surface) · Ask query events instrumented — one of the two genuinely unmeasured qualifying actions | Ranjith · Ashish | Utkarsh | 30 Sept | Audience · AI Layer | SPLIT 08-21 from the O4 AI row — consumer-facing Ask is an Audience capability; Engine Room keeps internal AI only
O2 | Retention Mechanisms | Pulse (social briefing) ENTERS the competition — legal gate closed + the 15-Jul team approval finally sent · candidate list named (alerts, community, report surfaces) | Ranjith (runs) · Utkarsh (scores Oct) | — | 30 Sept | Audience · Activate & Deepen | NEW — the competition's first entrants; scored on 30-day return lift in Oct
O2 | Data | Entity coverage: startups + investors adds (qualification layer) | Prapti | Utkarsh | 30 Sept | Audience · Measurement & Data Activation · coverage
O2 | Offering | A1 price probe RUN + READ on the legacy book (₹4,999–14,999 band, pooled ~20% bar) · ~38 lapsed data-buyers called | Ranjith + Utkarsh | — | 30 Sept | Audience · Offering | NEW — pre-registered bar: sample migrating below ~20% = tier prices rework before anything is built
O3 · IPs, EVENTS & COMMUNITIES
O3 | CTO Summit | Delivered end-to-end 30 Sept — identity, assets, marketing, 75+ tickets, experience | Vishvani (mktg) · Akshay (design) · Pooja (agenda) | Utkarsh | 30 Sept | IPs · Flagships & Editions | Akshay Day-60 outcome; first per-IP-GM-style edition. QAA measurable once events-sheets lane exists
O3 | D2CX | Convocation 22–23 Sept delivered · Basecamp 3–5 Oct prepped | Shantanu | Utkarsh | 23 Sept | IPs · Cohorts & Communities | Mid-VD join is the design cover
O3 | D2C Retreat | Retreat delivered 17–19 Sept · 30 qualified applications closed | Vishvani | Nityam, Utkarsh | 19 Sept | IPs · Flagships & Editions | "Qualified" = the QIA bar — same definition (QAA rule)
O3 | FAST42 | Marketing prep only — launch Oct, event FEB | Nityam | Utkarsh | prep | IPs · Flagships & Editions | Do NOT let a delivery row reappear for Dec
O4 · ENGINE ROOM
O4 | Design system | ≥2 repeat formats templated (T3→template) · pod intake running on the board | Akshay | Utkarsh | 30 Sept | Engine Room · Automation & Infra | The compounding metric
O4 | Automation | Newsletter automation live · invoicing/chat-support automation for IP ops (from Aug) | Animesh · Ashish | Utkarsh | 30 Sept | Engine Room · Automation & Infra
O4 | Infra | Azure migration close-out (if deferred from Aug at the kickoff item) | Ashish | Utkarsh | ⬜ per Aug decision | Engine Room · Automation & Infra | The Aug collision decision decides this row
O4 | AI | Internal-AI pilots — AI Data Requests + AI Research on Inc42 data | Prapti | Utkarsh | 30 Sept | Engine Room · Internal AI & Agent Platform | Prapti-deprioritisation rule holds. Consumer Ask split to the O2 AI (Ask) row
RULES (compact): 1· Protected tier — warehouse/measurement rows: raids are reported misses, not absorbed. 2· Prapti-deprioritisation — if the warehouse gets a date, something else of hers comes OFF. 3· Serves grammar = Engine · Track (· driver where QIA-touching); a row serving nothing is missing strategy or shouldn't exist — control-tower check flags orphans both ways.
O1 | Distribution | Citations tracking starts — feeds the perception KPI | Nityam | Utkarsh | 30 Sept | Brand & Distribution · Distribution | ADDED by the serves-check 08-21: committed in the FY27 plan, served by no row
O3 | IP Capability | Events-team sheets ask scoped — which events, which columns, who sends each cycle (the QAA instrument) | Utkarsh (ask) · events team (supply) | — | 30 Sept | IPs · IP Capability | ADDED by the serves-check 08-21: the QAA instrument's first concrete step